## EXAMPLE Construction Plan
CONSTRUCTION MANAGEMENT PROJECT PLAN TEMPLATE
PROJECT TITLE |  | START DATE |  | PROJECT DURATION
Design-Build Alpha Beta |  | 2024-01-02
PROJECT MANAGER |  | END DATE |  | in days
Peter B. |  | 2024-03-26 |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | PRE-PROJECT PLANNING | Not Started | John D. | 2024-01-02 | 2024-02-09 | 39
1A | Design | In Progress | Shawn S. | 2024-01-02 | 2024-01-11 | 10
1B | Permitting | Complete | Dawn L. | 2024-01-07 | 2024-01-11 | 5
1C | Consultation | Complete | Sarah C. | 2024-01-10 | 2024-02-23 | 45
1D |  | Not Started |  | 2024-01-10 | 2024-01-20 | 11
1E |  | On Hold |  | 2024-01-16 | 2024-01-29 | 14
1F |  | On Hold |  | 2024-01-19 | 2024-02-01 | 14
1G |  | In Progress |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT PLANNING | Not Started |  | 2024-01-28 | 2024-02-14 | 18
2A | Demolition | Complete |  | 2024-01-28 | 2024-02-06 | 10
2B | Excavation | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2C | Concrete | Complete |  | 2024-02-04 | 2024-02-12 | 9
2D | Framing | Not Started
2E | Roofing | On Hold
2F | Plumbing | On Hold
2G | HVAC | Complete
2H | Windows | Not Started
2I | A/V | In Progress
2J | Insulation | In Progress
2K | Drywall | In Progress
2L | Exterior | Not Started
2M | Appliances | On Hold
2N |  | Not Started
2O |  | Not Started
2P |  | Not Started |  | 2024-02-06 | 2024-02-14 | 9
3 | POST PROJECT | In Progress |  | 2024-02-18 | 2024-03-26 | 38
3A | Quality Control | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3B | Punch List Items | Not Started |  | 2024-02-18 | 2024-02-23 | 6
3C | Exit Survey | On Hold |  | 2024-02-18 | 2024-02-26 | 9
3D |  | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3E |  | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3F |  | Not Started
Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Constuction Project Plan
CONSTRUCTION MANAGEMENT PROJECT PLAN TEMPLATE
PROJECT TITLE |  | START DATE |  | PROJECT DURATION
PROJECT MANAGER |  | END DATE |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | PRE-PROJECT PLANNING | Not Started |  |  |  | 1
1A | Design | In Progress |  |  |  | 1
1B | Permitting | Complete |  |  |  | 1
1C | Consultation | Complete |  |  |  | 1
1D |  | Not Started |  |  |  | 1
1E |  | On Hold |  |  |  | 1
1F |  | On Hold |  |  |  | 1
1G |  | In Progress |  |  |  | 1
2 | PROJECT PLANNING | Not Started |  |  |  | 1
2A | Demolition | Complete |  |  |  | 1
2B | Excavation | In Progress |  |  |  | 1
2C | Concrete | Complete |  |  |  | 1
2D | Framing | Not Started
2E | Roofing | On Hold
2F | Plumbing | On Hold
2G | HVAC | Complete
2H | Windows | Not Started
2I | A/V | In Progress
2J | Insulation | In Progress
2K | Drywall | In Progress
2L | Exterior | Not Started
2M | Appliances | On Hold
2N |  | Not Started
2O |  | Not Started
2P |  | Not Started |  |  |  | 1
3 | POST PROJECT | In Progress |  |  |  | 1
3A | Quality Control | In Progress |  |  |  | 1
3B | Punch List Items | Not Started |  |  |  | 1
3C | Exit Survey | On Hold |  |  |  | 1
3D |  | Not Started |  |  |  | 1
3E |  | Not Started |  |  |  | 1
3F |  | Not Started
Not Started
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.