## EXAMPLE - IT Project Task List
IT PROJECT TASK LIST TEMPLATE
PROJECT NAME | PROJECT ALPHA |  |  | PROJECT MANAGER |  | Jamal J.
PROJECT DELIVERABLE | Project deliverable description …
SCOPE STATEMENT | Scope statement …
START DATE | MM/DD/YY | END DATE | MM/DD/YY | OVERALL PROGRESS |  | 30%
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Connections and locations | In Progress | Sean T. | 2024-01-02 | 2024-01-08 | 6 | Designate how new infrastructure will connect within existing infrastructure and where it will be located.
General access requirements | Complete | Kelly R. | 2024-01-04 | 2024-01-11 | 7 | Define number of users requiring simultaneous access, and list user communities (developers, IT, vendors, etc.).
Databases | On Hold | Adam S. | 2024-01-07 | 2024-01-11 | 4 | Describe databases - include versions required, memory requirements, etc.
Server requests | In Progress | Sean T. | 2024-01-10 | 2024-01-15 | 5
Operating systems | In Progress | Sean T. | 2024-01-13 | 2024-01-20 | 7
| Not Started |  | 2024-01-16 | 2024-01-29 | 13
| In Progress |  | 2024-01-19 | 2024-02-01 | 13
| In Progress |  | 2024-01-22 | 2024-02-09 | 18
| In Progress |  | 2024-01-25 | 2024-02-05 | 11
| In Progress |  | 2024-01-28 | 2024-02-06 | 9
| In Progress |  | 2024-01-31 | 2024-02-02 | 2
| In Progress |  | 2024-02-04 | 2024-02-12 | 8
| In Progress |  | 2024-02-06 | 2024-02-14 | 8
| In Progress |  | 2024-02-09 | 2024-02-17 | 8
| In Progress |  | 2024-02-18 | 2024-02-20 | 2
| In Progress |  | 2024-02-15 | 2024-02-23 | 8
| In Progress |  | 2024-02-18 | 2024-02-26 | 8
| In Progress |  | 2024-02-21 | 2024-02-29 | 8
| In Progress |  | 2024-02-24 | 2024-03-03 | 8
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - IT Project Task List
IT PROJECT TASK LIST TEMPLATE
PROJECT NAME | NAME |  |  | PROJECT MANAGER |  | Name
PROJECT DELIVERABLE | Project deliverable description …
SCOPE STATEMENT | Scope statement …
START DATE | MM/DD/YY | END DATE | MM/DD/YY | OVERALL PROGRESS |  | 0%
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| In Progress |  | 2024-01-02 | 2024-01-08 | 6
| Complete |  | 2024-01-04 | 2024-01-11 | 7
| On Hold |  | 2024-01-07 | 2024-01-11 | 4
| In Progress |  | 2024-01-10 | 2024-01-15 | 5
| In Progress |  | 2024-01-13 | 2024-01-20 | 7
| Not Started |  | 2024-01-16 | 2024-01-29 | 13
| In Progress |  | 2024-01-19 | 2024-02-01 | 13
| In Progress |  | 2024-01-22 | 2024-02-09 | 18
| In Progress |  | 2024-01-25 | 2024-02-05 | 11
| In Progress |  | 2024-01-28 | 2024-02-06 | 9
| In Progress |  | 2024-01-31 | 2024-02-02 | 2
| In Progress |  | 2024-02-04 | 2024-02-12 | 8
| In Progress |  | 2024-02-06 | 2024-02-14 | 8
| In Progress |  | 2024-02-09 | 2024-02-17 | 8
| In Progress |  | 2024-02-18 | 2024-02-20 | 2
| In Progress |  | 2024-02-15 | 2024-02-23 | 8
| In Progress |  | 2024-02-18 | 2024-02-26 | 8
| In Progress |  | 2024-02-21 | 2024-02-29 | 8
| In Progress |  | 2024-02-24 | 2024-03-03 | 8

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.