## EXAMPLE - RACI Gantt Chart
ITIL RACI TEMPLATE WITH GANTT CHART
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
|  | R | A | C | I
TASK | TASK | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE |  |  |  |  | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Service Management
1.1 | Service Strategy | Leon W | Sheree F | Pete S | Phil K | 2028-03-12 | 2028-03-15 | 4 | 100%
1.1.1 | Service Design | Kylie R | Steve L | Leon W | Mary D | 2028-03-15 | 2028-03-16 | 2 | 100%
1.2 | Service Transition | Pete S | Allen W | Kylie R | Gilbert G | 2028-03-15 | 2028-03-21 | 7 | 90%
1.3 | Service Operation | Steve L | Malik M | Kylie R | Alan P | 2028-03-16 | 2028-03-22 | 7 | 40%
1.4 | Capacity Management | Allen W | Malik M | Pete S | Billy W | 2028-03-17 | 2028-03-22 | 6 | 70%
1.5 | IT Service Review | Malik M | Kylie R | Malik M | Alfred H | 2028-03-18 | 2028-03-22 | 5 | 60%
1.6 | Information Security | Malik M | Pete S | David F | David L | 2028-03-23 | 2028-03-23 | 1 | 50%
2 | Change Management
2.1 | Choose Change Approach and Tools | Steve L | Pete S | Chip W | Jane C | 2028-03-24 | 2028-03-28 | 5 | 5%
2.2 | Developer ITCM Strategy | Allen W | Leon W | Fred S | Jean Luc G | 2028-03-29 | 2028-04-02 | 5 | 30%
2.3 | Conduct Coaching and Training | Malik M | Kylie R | Sheela E | Francois T |  |  |  | 0%
2.4 | Resolve Adoption Roadblocks | Malik M | Kylie R | Rhett B | Andre D |  |  |  | 0%
3 | Incident Management
3.1 | Review SLA | Pete S | Pete S | Kylie R | Anita H |  |  |  | 0%
3.2 | Adopt Incident Models | Leon W | Malik M | Kylie R | Billy W |  |  |  | 0%
3.2.1 | Define Incident Categories | Kylie R | Steve L | Pete S | Harrison C |  |  |  | 0%
3.2.2 | Review Incident Response Process | Kylie R | Allen W | Malik M | Wilma P |  |  |  | 0%
3.3 | Define Roles for ITIM | Pete S | Malik M | David F | Coco M |  |  |  | 0%
3.3.1 | Review Incident Security Practices | Malik M | Malik M | Anand G | Brett H |  |  |  | 0%
4 | Performance Management
4.1 | Project Objectives | Steve L | Kylie R | Raul M | Filbert S |  |  |  | 0%
4.2 | Quality Deliverables | Allen W | Kylie R | Sheena E | Deena D |  |  |  | 0%
4.3 | Effort & Cost Tracking | Malik M | Pete S | Rupert S | Favio C |  |  |  | 0%
4.4 | Project Performance | Malik M | Malik M | Stella S | Enrique T |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - RACI Gantt Chart
ITIL RACI TEMPLATE WITH GANTT CHART
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
|  | R | A | C | I
TASK | TASK | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE |  |  |  |  | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Service Management
1.1 | Service Strategy | [7 empty] | 100%
1.1.1 | Service Design | [7 empty] | 0%
1.2 | Service Transition | [7 empty] | 0%
1.3 | Service Operation | [7 empty] | 0%
1.4 | Capacity Management | [7 empty] | 0%
1.5 | IT Service Review | [7 empty] | 0%
1.6 | Information Security | [7 empty] | 0%
2 | Change Management
2.1 | Choose Change Approach and Tools | [7 empty] | 0%
2.2 | Developer ITCM Strategy | [7 empty] | 0%
2.3 | Conduct Coaching and Training | [7 empty] | 0%
2.4 | Resolve Adoption Roadblocks | [7 empty] | 0%
3 | Incident Management
3.1 | Review SLA | [7 empty] | 0%
3.2 | Adopt Incident Models | [7 empty] | 0%
3.2.1 | Define Incident Categories | [7 empty] | 0%
3.2.2 | Review Incident Response Process | [7 empty] | 0%
3.3 | Define Roles for ITIM | [7 empty] | 0%
3.3.1 | Review Incident Security Practices | [7 empty] | 0%
4 | Performance Management
4.1 | Project Objectives | [7 empty] | 0%
4.2 | Quality Deliverables | [7 empty] | 0%
4.3 | Effort & Cost Tracking | [7 empty] | 0%
4.4 | Project Performance | [7 empty] | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.