## EXAMPLE Project Folio Score
PROJECT PORTFOLIO SCORECARD TEMPLATE
PROJECT MANAGEMENT OVERVIEW
OVERVIEW |  |  | PLANNED | ACTUAL | PLANNED LESS ACTUAL | COMMENTARY |  | OVERALL RISK ANALYSIS OUTCOMES | OVERALL BUDGET IMPACT | OVERALL COST BENEFIT ANALYSIS
TOTAL NUMBER OF PROJECTS COMPLETE |  |  | 6 | 2 | 4 | We've completed two of the six projects planned through Q3.
TOTAL TIME TO MOBILIZE IN HOURS |  |  | 1800 | 720 | 1080 | Mobilization is occurring one day faster than planned through Q3.
TOTAL QUALITY INDEX MEASURES |  |  | 291 | 21 | 270
TOTAL PORTFOLIO COST SAVINGS |  |  | 8060 | 9130 | -1070 | The additional benefits gained in Project Alpha more than offset the overruns in Project Beta.
PROJECTS AND KEY PERFORMANCE INDICATORS (KPIs)
PROJECTS | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT ALPHA
Costs/Savings Realized ($) | LOW | YELLOW | 1200 | 430 | 770 | Chris K. | The cost savings continue to come in more than planned. |  |  |  | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | RED | 600 | 240 | 360 | Chris K. | The effort is less than budgeted. |  |  |  | MM/DD/YY
Quality Index (1-100) | HIGH | GREY | 97 | 7 | 90 | Greta L. | #1 in sight by EOY on current growth trend |  |  |  | MM/DD/YY
Key Performance Measure | LOW | GREEN | [8 empty] | MM/DD/YY
Key Performance Measure | HIGH | GREEN | [8 empty] | MM/DD/YY
PROJECT BETA
Costs/Savings Realized ($) | HIGH | YELLOW | 5560 | 6200 | -640 | Chris K. | Cost overruns are because the work is more complex than anticipated. |  |  |  | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | GREY | 600 | 240 | 360 | Chris K. | The effort involved in Project Beta continues to be more than planned. |  |  |  | MM/DD/YY
Quality Index (1-100) | ON HOLD | GREEN | 97 | 7 | 90 | Greta L. | Our QA processes are currently under review. |  |  |  | MM/DD/YY
Key Performance Measure | MEDIUM | GREEN | [8 empty] | MM/DD/YY
Key Performance Measure | HIGH | YELLOW | [8 empty] | MM/DD/YY
PROJECT SIGMA
Costs/Savings Realized ($) | MEDIUM | GREEN | 1300 | 2500 | -1200 | Chris K. |  |  |  |  | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | RED | 600 | 240 | 360 | Chris K. |  |  |  |  | MM/DD/YY
Quality Index (1-100) | ON HOLD | GREY | 97 | 7 | 90 | Greta L. |  |  |  |  | MM/DD/YY
Key Performance Measure | HIGH | YELLOW | [8 empty] | MM/DD/YY
Key Performance Measure | MEDIUM | GREEN | [8 empty] | MM/DD/YY
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Folio Scorecard
PROJECT PORTFOLIO SCORECARD TEMPLATE
PROJECT MANAGEMENT OVERVIEW
OVERVIEW |  |  | PLANNED | ACTUAL | PLANNED LESS ACTUAL | COMMENTARY |  | OVERALL RISK ANALYSIS OUTCOMES | OVERALL BUDGET IMPACT | OVERALL COST BENEFIT ANALYSIS
TOTAL NUMBER OF PROJECTS COMPLETE |  |  | 0 | 0 | 0
TOTAL TIME TO MOBILIZE IN HOURS |  |  | 0 | 0 | 0
TOTAL QUALITY INDEX MEASURES |  |  | 0 | 0 | 0
TOTAL PORTFOLIO COST SAVINGS |  |  | 0 | 0 | 0
PROJECTS AND KEY PERFORMANCE INDICATORS (KPIs)
PROJECTS | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT ALPHA
Costs/Savings Realized ($) | LOW | YELLOW | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | RED | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Quality Index (1-100) | HIGH | GREY | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Key Performance Measure | LOW | GREEN | [8 empty] | MM/DD/YY
Key Performance Measure | HIGH | GREEN | [8 empty] | MM/DD/YY
PROJECT BETA
Costs/Savings Realized ($) | HIGH | YELLOW | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | GREY | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Quality Index (1-100) | ON HOLD | GREEN | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Key Performance Measure | MEDIUM | GREEN | [8 empty] | MM/DD/YY
Key Performance Measure | HIGH | YELLOW | [8 empty] | MM/DD/YY
PROJECT SIGMA
Costs/Savings Realized ($) | MEDIUM | GREEN | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Scheduled Hours (hours) | MEDIUM | RED | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Quality Index (1-100) | ON HOLD | GREY | 0 | 0 | 0 | [5 empty] | MM/DD/YY
Key Performance Measure | HIGH | YELLOW | [8 empty] | MM/DD/YY
Key Performance Measure | MEDIUM | GREEN | [8 empty] | MM/DD/YY

## Dropdown Keys - do not delete
DROPDOWN KEYS (DO NOT DELETE)
PRIORITY | STATUS
HIGH | GREEN
MEDIUM | YELLOW
LOW | RED
ON HOLD | GREY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.