## EXAMPLE Project Task List
PROJECT TASK LIST WITH GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
Project Alpha | Laura L. | 2026-09-02 | 2027-10-10 |  | 20%
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
Set Kick-Off Meeting | Alex B. | 2022-09-02 | 2022-09-03 | 1 | Complete
Agree on Objectives | Frank C. | 2022-09-03 | 2022-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2022-09-07 | 2022-09-12 | 5 | Complete
Hardware Reqs. | Jacob S. | 2022-09-09 | 2022-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2022-09-11 | 2022-09-15 | 4 | In Progress
Staffing | Alex B. | 2022-09-16 | 2022-09-17 | 1 | In Progress
Technical Reqs. | Frank C. | 2022-09-17 | 2022-09-21 | 4 | Not Started
DB Development | Shari W. | 2022-09-22 | 2022-09-24 | 2 | Not Started
API Development | Shari W. | 2022-09-23 | 2022-09-27 | 4 | Not Started
UI Client | Alex B. | 2022-09-25 | 2022-09-29 | 4 | Not Started
Testing | Kennedy K. | 2022-09-24 | 2022-10-02 | 8 | Not Started
Dev. Complete | Jacob S. | 2022-10-02 | 2022-10-05 | 3 | Not Started
Hardware Config. | Alex B. | 2022-10-05 | 2022-10-07 | 2 | Not Started
System Testing | Kennedy K. | 2022-10-06 | 2022-10-09 | 3 | Not Started
LAUNCH |  | 2022-10-09 | 2022-10-10 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Task List
PROJECT TASK LIST WITH GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
0%
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Overdue
|  |  |  | 0 | In Progress
|  |  |  | 0 | In Progress
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
|  |  |  | 0 | Not Started
LAUNCH |  |  |  | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.