## Crashing CPM Time and Cost Calc
EASY PROJECT CRASHING CPM TIME AND COST CALCULATOR
Shaded cells contain formulas; do not alter. **User to enter sum of Actual Crash Cost per each Activity included in the Network Path to calculate the PATH COMPLETION TIME. |  |  | NORMAL SCHEDULE | DEADLINE | TOTAL CRASH COST
|  |  | 127 | 75 | 37471.0784
ID | ACTIVITY | PRECED. | NORMAL DURATION | CRASH DURATION | NORMAL COST | CRASH COST | CRASH COST PER DAY
A | Design | --- | 30 | 15 | 4000 | 6200 | 146.6667
B | Supply Ordering | A | 20 | 3 | 400 | 500 | 5.8824
C | Metal and Electrical Manufacture | B | 25 | 13 | 5000 | 7500 | 208.3333
D | Manuals | B | 15 | 12 | 6200 | 7800 | 533.3333
E | Assembly | C | 30 | 18 | 4300 | 5200 | 75
F | Testing | D | 5 | 4 | 3000 | 3300 | 300
G | Delivery to Customer | E,F | 10 | 6 | 7100 | 8350 | 312.5
|  |  |  | TOTAL NORMAL COST | 30000 | 38850 | 1581.7157
|  | This is the maximum number of days available for each crash activity. | Find the optimal number of days to crash per activity to minimize add'l costs. |  |  |  | Sum of Actual Crash Cost per each Activity in the Network Path.
ID | ACTIVITY | MAXIMUM CRASH DAYS | NUMBER OF DAYS CRASHED | ACTUAL CRASH COST | ACTUAL ACTIVITY DURATION | NETWORK PATHS | PATH COMPLETION TIME
A | Design | 15 | 15 | 2200 | 15 | A B C E G | 71
B | Supply Ordering | 17 | 5 | 29.4118 | 15 | A B D F G | 55
C | Metal and Electrical Manufacture | 12 | 12 | 2500 | 13
D | Manuals | 3 | 2 | 1066.6667 | 13
E | Assembly | 12 | 10 | 750 | 20
F | Testing | 1 | 1 | 300 | 4
G | Delivery to Customer | 4 | 2 | 625 | 8
|  |  | TOTAL CRASH COST | 7471.0784 | PROJECT COMPLETION TIME |  | 71
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Calculator
PROJECT CRASHING CPM TIME AND COST CALCULATOR
Shaded cells contain formulas; do not alter. **User to enter sum of Actual Crash Cost per each Activity included in the Network Path to calculate the PATH COMPLETION TIME. |  |  | NORMAL SCHEDULE | DEADLINE | TOTAL CRASH COST
0
ID | ACTIVITY | PRECED. | NORMAL DURATION | CRASH DURATION | NORMAL COST | CRASH COST | CRASH COST PER DAY
A |  | ---
B |  | A
C |  | B
D
E
F
G
H
I
J
K
L
|  |  |  | TOTAL NORMAL COST | 0 | 0 | 0
|  | This is the maximum number of days available for each crash activity. | Find the optimal number of days to crash per activity to minimize add'l costs. |  |  |  | Sum of Actual Crash Cost per each Activity in the Network Path.
ID | ACTIVITY | MAXIMUM CRASH DAYS | NUMBER OF DAYS CRASHED | ACTUAL CRASH COST | ACTUAL ACTIVITY DURATION | NETWORK PATHS | PATH COMPLETION TIME
A | 0 | 0 |  |  | 0
B | 0 | 0 |  |  | 0
C | 0 | 0 |  |  | 0
D | 0 | 0 |  |  | 0
E | 0 | 0 |  |  | 0
F | 0 | 0 |  |  | 0
G | 0 | 0 |  |  | 0
H | 0 | 0 |  |  | 0
I | 0 | 0 |  |  | 0
J | 0 | 0 |  |  | 0
K | 0 | 0 |  |  | 0
L | 0 | 0 |  |  | 0
|  |  | TOTAL CRASH COST | 0 | PROJECT COMPLETION TIME |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.