## EXAMPLE - IT Risk Register
IT RISK REGISTER TEMPLATE EXAMPLE
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF/THEN STATEMENT) | RISK TRIGGER | PROBABILITY | IMPACT | RISK SEVERITY SCORE | MITIGATION/RESPONSE PLAN | STATUS OF MITIGATION/RESPONSE | OWNER | OTHER NOTES
1 | MM/DD/YY | Category 1 | If a third-party vendor fails to meet their service-level agreement (SLA) to build an important component of the software, then there will be delays. | A third-party vendor fails to complete the requirements laid out in the SLA. | 1 | 8 | 8 | The project team vendor liaison will establish a plan during the service-level agreement drafting phase to stay in continual contact with the vendor as they develop their component. | The backup plan has been established; communications with the vendor are ongoing; the development of the software component is on schedule | Elena Ramirez, project team vendor liaison
2 | MM/DD/YY | Category 2 | If the software requirements are unclear or misunderstood by the client or software development team, then the client will be dissatisfied with the product. | A dispute arises between the client and the software development team during the testing phase. | 2 | 4 | 8 | The software development team will work with the client to develop a detailed outline of all software expectations. They will continually revisit this outline the the client throughout the project. | Planning documents have been completed with details on specifications; the project team is continually meeting with client representatives. | Jeff Petersen, client liaison
3 | MM/DD/YY | Category 3 | If we lose key software developers for any reason, then there will be expected delays in finding and training replacement developers. | A developer announces that they are leaving the team. | 2 | 8 | 16 | Each key developer will maintain a project log and training document to decrease the training time for potential new developers; the project manager will schedule time for mentor training and team update meetings so that other members of the team can step in if/when a developer leaves. | Conversations with developers are ongoing; mentorship plans and training are in development; the team is meeting regularly to discuss individual work. | Amir Muhammad, human resources project lead
4 | MM/DD/YY | Category 4 | If there are regulatory compliance violations, then we may face penalties or delays. | A team member identifies a regulatory compliance violation during their regular checks. | 1 | 2 | 2 | The project manager will assemble a subgroup to monitor all existing regulations and research new regulations as they come up. They will also create a plan for addressing regulations. | The team is on track to comply with all regulations. | Susan Perkins, regulatory compliance subteam lead
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - IT Risk Register
IT RISK REGISTER TEMPLATE
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF/THEN STATEMENT) | RISK TRIGGER | PROBABILITY | IMPACT | RISK SEVERITY SCORE | MITIGATION/RESPONSE PLAN | STATUS OF MITIGATION/RESPONSE | OWNER | OTHER NOTES
1 | MM/DD/YY |  |  |  | 1 | 1 | 1
2 | MM/DD/YY |  |  |  | 1 | 1 | 1
3 | MM/DD/YY |  |  |  | 1 | 1 | 1
4 | MM/DD/YY |  |  |  | 1 | 1 | 1
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4
[5 empty] | 2 | 2 | 4

## Risk Key - DO NOT DELETE
RISK KEY - DO NOT DELETE
PROBABILITY | IMPACT
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.