## EXAMPLE - Agile Software Gantt
AGILE SOFTWARE ENGINEERING GANTT CHART TEMPLATE EXAMPLE
PROJECT NAME |  | PROJECT MANAGER |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS | PROJECT DELIVERABLE
Product Release |  | Alex B. |  | 20% | 2028-09-02 | 2028-10-10 | 38 | Deliverable
SCOPE STATEMENT
Scope statement
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-02 | 2022-09-03 | 1 | COMPLETE
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | IN PROGRESS
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | ON HOLD
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-11 | 2 | COMPLETE
| Sprint 2 |  | Jacob S. |  | 2022-09-11 | 2022-09-15 | 4 | OVERDUE
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | NOT STARTED
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | NOT STARTED
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | COMPLETE
| Sprint 3 |  | Shari W. |  | 2022-09-23 | 2022-09-27 | 4 | COMPLETE
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | COMPLETE
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | COMPLETE
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | COMPLETE
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Agile Software Gantt
AGILE SOFTWARE ENGINEERING GANTT CHART TEMPLATE
PROJECT NAME |  | PROJECT MANAGER |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS | PROJECT DELIVERABLE
Name |  | Name |  | 0% |  |  | 0 | Deliverable
SCOPE STATEMENT
Scope statement
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | COMMENTS
| Sprint 1 | [5 empty] | 0 | COMPLETE
| Feature 1 | [5 empty] | 0 | IN PROGRESS
| Feature 2 | [5 empty] | 0 | ON HOLD
| Feature 3 | [5 empty] | 0 | COMPLETE
| Sprint 2 | [5 empty] | 0 | OVERDUE
| Feature 4 | [5 empty] | 0 | NOT STARTED
| Feature 5 | [5 empty] | 0 | NOT STARTED
| Feature 6 | [5 empty] | 0 | COMPLETE
| Sprint 3 | [5 empty] | 0 | COMPLETE
| Feature 7 | [5 empty] | 0 | COMPLETE
| Feature 8 | [5 empty] | 0 | COMPLETE
| Feature 9 | [5 empty] | 0 | COMPLETE
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS KEY
COMPLETE
IN PROGRESS
ON HOLD
OVERDUE
NOT STARTED

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.