## SAMPLE Biz Plan Gantt Chart
SAMPLE BUSINESS PLAN GANTT CHART TEMPLATE
PROJECT |  |  | START DATE
|  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
[6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
TASKS | TASK OWNER | STATUS | START | END | DAYS | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17
Phase 1: Assess the Need |  | Complete | 2025-09-02 | 2025-09-05 | 4 |  | A | A | A | A
Clearly identify the problem and solution |  | On Hold | 2025-09-02 | 2025-09-02 | 1 |  | A
Research existing alternatives |  | In Progress | 2025-09-02 | 2025-09-02 | 1 |  | A
Pinpoint gaps in existing products or services |  | Overdue | 2025-09-03 | 2025-09-03 | 1 |  |  | A
Determine skills, equipment, and materials needed |  | Needs Review | 2025-09-04 | 2025-09-04 | 1 |  |  |  | A
Decide whether to proceed |  | Needs Update | 2025-09-05 | 2025-09-05 | 1 |  |  |  |  | A
Phase 2: Find Opportunity and Check Viability |  | In Progress | 2025-09-05 | 2025-09-19 | 11 |  |  |  |  | A | A | A | A | A | A | A | A | A | A | A
Define your mission |  | Complete | 2025-09-05 | 2025-09-05 | 1 |  |  |  |  | A
Research market |  | Complete | 2025-09-05 | 2025-09-05 | 1 |  |  |  |  | A
Conduct interviews with stakeholders and SMEs |  | Canceled | 2025-09-08 | 2025-09-12 | 5 | [5 empty] | A | A | A | A | A
Identify needed resources |  | Complete | 2025-09-11 | 2025-09-15 | 3 | [8 empty] | A | A | A
Identify startup costs |  | Complete | 2025-09-15 | 2025-09-16 | 2 | [10 empty] | A | A
Identify operating costs |  | Complete | 2025-09-15 | 2025-09-16 | 2 | [10 empty] | A | A
Determine sources of funding |  | Complete | 2025-09-17 | 2025-09-17 | 1 | [12 empty] | A
Assess profitability |  | Complete | 2025-09-18 | 2025-09-19 | 2 | [13 empty] | A | A
Phase 3: Evaluate Potential Risks |  | Complete | 2025-09-15 | 2025-09-25 | 9 | [10 empty] | A | A | A | A | A | A | A | A | A
Assess market size |  | Complete | 2025-09-15 | 2025-09-17 | 3 | [10 empty] | A | A | A
Estimate competition |  | Complete | 2025-09-17 | 2025-09-18 | 2 | [12 empty] | A | A
Conduct SWOT Analysis |  | Complete | 2025-09-18 | 2025-09-19 | 2 | [13 empty] | A | A
Assess economic climate |  | Complete | 2025-09-19 | 2025-09-23 | 3 | [14 empty] | A | A | A
Develop strategic plan |  | Complete | 2025-09-24 | 2025-09-25 | 2 | [17 empty] | A | A
Phase 4: Attract Stakeholders |  | Complete | 2025-09-25 | 2025-10-07 | 9 | [18 empty] | A | A | A | A | A | A | A | A | A
Establish management team |  | Complete | 2025-09-25 | 2025-09-29 | 3 | [18 empty] | A | A | A
Seek strategic partnerships |  | Complete | 2025-09-30 | 2025-10-03 | 4 | [21 empty] | A | A | A | A
Develop outreach plan |  | Complete | 2025-10-03 | 2025-10-07 | 3 | [24 empty] | A | A | A
Phase 5: Prepare and Pitch Business Plan |  | Complete | 2025-09-25 | 2025-10-07 | 9 | [18 empty] | A | A | A | A | A | A | A | A | A
Create business plan outline |  | Complete | 2025-09-25 | 2025-09-29 | 3 | [18 empty] | A | A | A
Fill in each section of business plan |  | Complete | 2025-09-30 | 2025-10-03 | 4 | [21 empty] | A | A | A | A
Develop investor pitch deck |  | Complete | 2025-10-03 | 2025-10-07 | 3 | [24 empty] | A | A | A
Phase 6: Establish Supporting Systems |  | Complete | 2025-10-07 | 2025-10-14 | 6 | [26 empty] | A | A | A | A | A | A
Create bookkeeping systems |  | Complete | 2025-10-07 | 2025-10-08 | 2 | [26 empty] | A | A
Create Manuals and Policies |  | Complete | 2025-10-08 | 2025-10-10 | 3 | [27 empty] | A | A | A
Create company portal to store key documents |  | Complete | 2025-10-10 | 2025-10-14 | 3 | [29 empty] | A | A | A
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Biz Plan Gantt Chart
BUSINESS PLAN GANTT CHART TEMPLATE
PROJECT |  |  | START DATE
|  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded fields only. | [5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASKS | TASK OWNER | STATUS | START DATE | END DATE | DAYS | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16
|  |  | 0 | 0 | 0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
|  |  | 0 | 0 | 0
0
0
0

## Status Keys - DO NOT DELETE
Drop Down Keys - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review
Needs Update
Canceled

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.