**[](https://www.smartsheet.com/try-it?trp=11631&utm_source=integrated-content&utm_campaign=/content/gantt-chart-examples&utm_medium=Clinical+Trial+Project+Gantt+Chart+Example+doc+11631&lpa=Clinical+Trial+Project+Gantt+Chart+Example+doc+11631)SAMPLE CLINICAL TRIAL PROJECT GANTT CHART TEMPLATE**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROJECT NAME | PROJECT LEAD | PROJECT START DATE | PROJECT END DATE | TODAY’S DATE |
| Project Alpha | Kent P. | MM/DD/YY | MM/DD/YY | MM/DD/YY |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | **PHASE ONE** | | | **PHASE TWO** | | | **PHASE THREE** | | | **PHASE FOUR** | | |
| **TASK ID** | **TASK** | **% DONE** | **ASSIGNED TO** | **START DATE** | **END DATE** | **WEEK**  **1** | **WEEK**  **2** | **WEEK**  **3** | **WEEK**  **4** | **WEEK**  **5** | **WEEK**  **6** | **WEEK**  **7** | **WEEK**  **8** | **WEEK**  **9** | **WEEK**  **10** | **WEEK**  **11** | **WEEK**  **12** |
| 1 | Choose research questions and study design | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Choose outcomes | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Register the trial | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Obtain ethics approval (IRB) | 90% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Prospectively publish protocol | 40% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Logistical planning for trial and data management | 25% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Recruitment and retention plan | 5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Identify and manage trial sites and staff | 30% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Data collection | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Data analysis | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Finding dissemination | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Task Name | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Task Name | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |
| --- |
| **DISCLAIMER**  Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |