## SAMPLE Construction Gantt Chart
SAMPLE CONSTRUCTION PROJECT GANTT CHART TEMPLATE
PROJECT NAME |  |  |  | PROJECT LOCATION | START DATE
Project Alpha |  |  |  | Address, City, State ZIP | 2027-10-01
PROJECT MANAGER |  |  |  |  | END DATE
John K. |  |  |  |  | 2028-06-01
TIMELINE
TASK NAME | START DATE | END DATE | DURATION in days
Demo Prep | 2027-10-01 | 2027-10-06 | 6
Demolition | 2027-10-06 | 2027-10-24 | 19
Excavation | 2027-10-25 | 2027-10-29 | 5
Concrete | 2027-11-01 | 2027-11-13 | 13
Pre backfill | 2027-11-13 | 2027-11-15 | 3
Framing | 2027-10-25 | 2027-12-05 | 42
Roof | 2027-11-19 | 2027-12-10 | 22
Plumbing | 2027-10-29 | 2027-12-09 | 42
Windows | 2027-11-22 | 2027-12-15 | 24
HVAC | 2027-11-29 | 2027-12-20 | 22
Electrical | 2027-12-10 | 2027-12-22 | 13
A/V | 2027-12-10 | 2027-12-15 | 6
House wrap | 2027-12-27 | 2027-12-30 | 4
Insulation | 2027-12-03 | 2027-12-21 | 19
Drywall | 2028-01-03 | 2028-01-23 | 21
Exterior stone | 2028-01-03 | 2028-01-21 | 19
Exterior case work | 2028-01-04 | 2028-01-13 | 10
Laundry/furnace room flooring | 2028-02-16 | 2028-03-11 | 25
Hardwoods | 2028-01-19 | 2028-03-10 | 52
Tile | 2028-02-03 | 2028-02-14 | 12
Cabinets | 2028-01-22 | 2028-03-06 | 45
Plumbing -hang sinks | 2028-02-16 | 2028-02-23 | 8
Interior doors | 2028-02-25 | 2028-03-09 | 14
Millwork | 2028-02-15 | 2028-02-21 | 7
Interior painting | 2028-02-28 | 2028-04-14 | 47
Stone Counters | 2028-03-21 | 2028-03-31 | 11
Schedule Buffer | 2028-02-28 | 2028-03-10 | 12
Decks | 2028-02-28 | 2028-03-22 | 24
Interior doors- hang & hardware | 2028-04-03 | 2028-04-13 | 11
Appliances | 2028-04-12 | 2028-05-03 | 22
Plumbing | 2028-05-02 | 2028-05-05 | 4
Electrical | 2028-05-03 | 2028-05-11 | 9
Bathroom Glass | 2028-05-09 | 2028-05-13 | 5
Garage Door dress up | 2028-05-13 | 2028-05-22 | 10
FINAL Inspections | 2028-05-02 | 2028-05-02 | 1
Wrap up | 2028-05-09 | 2028-05-29 | 21
House Cleaning | 2028-05-27 | 2028-05-30 | 4
Complete | 2028-06-01 | 2028-06-01 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Construction Gantt Chart
CONSTRUCTION PROJECT GANTT CHART TEMPLATE
PROJECT NAME |  |  |  | PROJECT LOCATION | START DATE
PROJECT MANAGER |  |  |  |  | END DATE
TIMELINE
TASK NAME | START DATE | END DATE | DURATION in days
Task |  |  | 1
Task |  |  | 1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.