## EXAMPLE Digital Marketing Gantt
DIGITAL MARKETING CAMPAIGN GANTT CHART TEMPLATE EXAMPLE
START DATE
2025-01-01
[5 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
CAMPAIGN TYPE | PROJECT GOALS | START DATE | END DATE | # of Days | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
NATIONAL MARKETING |  | 2025-01-05 | 2026-04-21 | 337 | bar: 2025-01-01 to 2027-12-01
Banner Ads |  | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
Task 2 |  | 2025-04-02 | 2025-08-31 | 108 | bar: 2025-04-01 to 2025-08-01
Task 3 |  | 2025-07-11 | 2025-10-15 | 69 | bar: 2025-07-01 to 2025-10-01
Task 4 |  | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-12-01
Task 5 |  | 2026-01-05 | 2026-03-11 | 48 | bar: 2026-01-01 to 2026-03-01
Task 6 |  | 2026-03-12 | 2026-04-21 | 29 | bar: 2026-03-01 to 2026-04-01
LOCAL MARKETING |  | 2025-04-22 | 2026-08-15 | 344 | bar: 2025-01-01 to 2027-12-01
Web ads |  | 2025-04-22 | 2025-09-21 | 109 | bar: 2025-04-01 to 2025-09-01
Social media ads |  | 2025-05-30 | 2025-11-02 | 111 | bar: 2025-05-01 to 2025-11-01
Task 3 |  | 2025-08-05 | 2025-12-19 | 99 | bar: 2025-08-01 to 2025-12-01
Task 4 |  | 2025-10-25 | 2025-10-31 | 5 | bar: 2025-10-01
Task 5 |  | 2025-10-25 | 2026-03-26 | 109 | bar: 2025-10-01 to 2026-03-01
Task 6 |  | 2025-12-01 | 2026-08-15 | 185 | bar: 2025-12-01 to 2026-08-01
PUBLIC RELATIONS |  | 2026-02-14 | 2027-02-28 | 270 | bar: 2025-01-01 to 2027-12-01
Press releases |  | 2026-02-14 | 2026-02-28 | 10 | bar: 2026-02-01
Webinars |  | 2026-02-28 | 2026-06-28 | 85 | bar: 2026-02-01 to 2026-06-01
Task 3 |  | 2026-03-02 | 2026-06-28 | 85 | bar: 2026-03-01 to 2026-06-01
Task 4 |  | 2026-06-28 | 2026-07-11 | 10 | bar: 2026-06-01 to 2026-07-01
Task 5 |  | 2026-07-14 | 2026-09-27 | 54 | bar: 2026-07-01 to 2026-09-01
Task 6 |  | 2026-10-01 | 2027-02-28 | 107 | bar: 2026-10-01 to 2027-02-01
CONTENT MARKETING |  | 2026-12-01 | 2027-07-01 | 153 | bar: 2025-01-01 to 2027-12-01
Sponsored content |  | 2026-12-01 | 2027-02-28 | 64 | bar: 2026-12-01 to 2027-02-01
Landing page |  | 2027-01-01 | 2027-03-31 | 64 | bar: 2027-01-01 to 2027-03-01
White papers / eBooks |  | 2027-03-25 | 2027-07-01 | 71 | bar: 2027-03-01 to 2027-07-01
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
SOCIAL MEDIA |  | 0 | 0 | 0
TikTok |  |  |  | 0
Facebook |  |  |  | 0
Pinterest |  |  |  | 0
Instagram |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-01-01 to 2025-12-01

## BLANK Digital Marketing Gantt
DIGITAL MARKETING CAMPAIGN GANTT CHART TEMPLATE
START DATE
2025-01-01 | <-- Enter initial Start Date to populate Timeline dates.
Enter each Task Start and End Date per Project, below. Project Dates and # of Days will calculate automatically. |  |  |  |  | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
CAMPAIGN TYPE | PROJECT GOALS | START DATE | END DATE | # of Days | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
CAMPAIGN ONE |  |  |  | 0
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
CAMPAIGN TWO |  |  |  | 0
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
CAMPAIGN THREE |  |  |  | 0
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
CAMPAIGN FOUR |  |  |  | 0
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0
CAMPAIGN FIVE |  |  |  | 0
Task 1 |  |  |  | 0
Task 2 |  |  |  | 0
Task 3 |  |  |  | 0
Task 4 |  |  |  | 0
Task 5 |  |  |  | 0
Task 6 |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.