## EXAMPLE Email Marketing Gantt
EMAIL MARKETING CAMPAIGN GANTT CHART TEMPLATE EXAMPLE
PROJECT TITLE
Project Beta
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
William B. |  | Valley View Inc. |  |  |  | MM/DD/YY
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Kick-off
1.1 | Campaign Approved | Leon W | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 | Kick-off Meeting | Kylie R | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 | Resourcing Plan | Pete S | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 | Execution Plan Completed | Steve L | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 |  | Allen W | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 |  | Malik M | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 |  | Malik M | 2026-03-23 | 2026-03-23 | 1 | 50%
2 | Testing & Audience
2.1 | Testing Strategies | Steve L | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 | Define Customer or Prospective Segments | Allen W | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | Size (Audience) | Malik M |  |  |  | 0%
2.4 | Target and Test Matrices Finalized and Accepted | Malik M |  |  |  | 0%
3 | Develop: Integrated Channel Campaign
3.1 | Email(s) | Pete S |  |  |  | 0%
3.2 | Landing Page(s) | Leon W |  |  |  | 0%
3.2.1 | Confirmation, Thank you, Follow-up emails | Kylie R |  |  |  | 0%
3.2.2 | Final Creative Briefs Submitted | Kylie R |  |  |  | 0%
3.3 | Content / Creative Development | Pete S |  |  |  | 0%
3.3.1 | Lead Response Plan | Malik M |  |  |  | 0%
4 | Pre-launch Audits
4.1 | Audience, Segments, Tests | Steve L |  |  |  | 0%
4.2 |  | Allen W |  |  |  | 0%
4.3 |  | Malik M |  |  |  | 0%
4.4 |  | Malik M |  |  |  | 0%
5 | Launch
5.1 | Channel A |  |  |  |  | 0%
5.2 | Channel B |  |  |  |  | 0%
5.3 | Channel C |  |  |  |  | 0%
5.4 | Channel D |  |  |  |  | 0%
6 | Measurement
6.1 | Key Metrics Channel A |  |  |  |  | 0%
6.2 | Key Metrics Channel B |  |  |  |  | 0%
6.3 | Performance Evaluation |  |  |  |  | 0%
6.4 | Plan Refinement |  |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Email Marketing Gantt
EMAIL MARKETING CAMPAIGN GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 |  |  | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 |  |  | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 |  |  | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 |  |  | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 |  |  | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 |  |  | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 |  |  | 2026-03-23 | 2026-03-23 | 1 | 50%
2
2.1 |  |  | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 |  |  | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.2.1 | [5 empty] | 0%
3.2.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.3.1 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%
5
5.1 | [5 empty] | 0%
5.2 | [5 empty] | 0%
5.3 | [5 empty] | 0%
5.4 | [5 empty] | 0%
6
6.1 | [5 empty] | 0%
6.2 | [5 empty] | 0%
6.3 | [5 empty] | 0%
6.4 | [5 empty] | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.