## EXAMPLE Onboarding Gantt Chart
EMPLOYEE ONBOARDING GANTT CHART TEMPLATE EXAMPLE
EMPLOYEE NAME |  |  |  | START DATE
Keisha T. |  |  |  | MM/DD/YY
PROJECT MANAGER |  |  |  | END DATE
Thomas L. |  |  |  | MM/DD/YY
| TIMELINE |  |  | PROJECT NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Finalize start date | 2025-05-05 | 2025-07-01 | 58 |  | 0
Brief employee on schedule and job duties | 2025-05-10 | 2025-08-10 | 93 |  | 0
Schedule meetings with critical team members | 2025-06-10 | 2026-03-01 | 265 |  | 0
Clean work space | 2025-06-22 | 2025-08-04 | 44 |  | 0
Order office and building keys | 2025-07-14 | 2025-11-01 | 111 |  | 0
Order business cards | 2025-07-14 | 2026-01-20 | 191
Add employee to relevant mailing lists | 2025-08-01 | 2025-10-01 | 62
Order required tech | 2025-08-14 | 2025-08-30 | 17
IT set up | 2025-09-01 | 2025-12-10 | 101
Arrange for drive access | 2025-10-01 | 2025-11-15 | 46
Arrange for phone installation | 2025-10-01 | 2025-12-01 | 62
Create 90-day training plan | 2025-11-01 | 2025-12-01 | 31
Schedule appropriate trainings | 2025-11-10 | 2025-12-10 | 31
First day onboarding activities | 2025-12-01 | 2026-02-10 | 72
DELIVERY TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Onboarding Gantt Chart
EMPLOYEE ONBOARDING GANTT CHART TEMPLATE
EMPLOYEE NAME |  |  |  | START DATE
Name |  |  |  | MM/DD/YY
PROJECT MANAGER |  |  |  | END DATE
Name |  |  |  | MM/DD/YY
| TIMELINE |  |  | PROJECT NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
|  |  | 1 |  | 0
1
1
1
1
1
1
1
1
1
DELIVERY TIMELINE
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.