## EXAMPLE - Event Marketing Gantt
EVENT MARKETING GANTT CHART TEMPLATE EXAMPLE
EVENT NAME | [7 empty] | EVENT DATE
Company Mixer | [7 empty] | MM/DD/YY
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE |  | EVENT DESCRIPTION
John K. |  | Weller Corp. |  |  |  | MM/DD/YY |  | Annual corporate fundraiser
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | National Marketing
1.1 | Establish Goals | Leon W | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 | Banner Ads | Kylie R | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 | Develop Creative Concept | Pete S | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 | Identify Marketing Channels | Steve L | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 | Budget and Financial Projection | Allen W | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 | Set up Campaign Calendar | Malik M | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 | Creative Brief | Malik M | 2026-03-23 | 2026-03-23 | 1 | 50%
2 | Local Marketing
2.1 | Message Planning | Steve L | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 | Create Marketing Assets | Allen W | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | Web Ads | Malik M |  |  |  | 0%
2.4 | Other | Malik M |  |  |  | 0%
3 | Public Relations
3.1 | Email Campaign | Pete S |  |  |  | 0%
3.2 | Social Media | Leon W |  |  |  | 0%
3.2.1 | Sales Outreach | Kylie R |  |  |  | 0%
3.2.2 | Press Release | Kylie R |  |  |  | 0%
3.3 | Print Advertising | Pete S |  |  |  | 0%
3.3.1 | Other | Malik M |  |  |  | 0%
4 | Content Marketing
4.1 | Sponsored Content | Steve L |  |  |  | 0%
4.2 | Landing Page | Allen W |  |  |  | 0%
4.3 | White papers / e-books | Malik M |  |  |  | 0%
4.4 | Other | Malik M |  |  |  | 0%
5 | Online
5.1 | Blog |  |  |  |  | 0%
5.2 | Website |  |  |  |  | 0%
5.3 | Mobile app |  |  |  |  | 0%
5.4 | E-newsletter |  |  |  |  | 0%
6 | Measurement
6.1 | Key Metrics Channel A |  |  |  |  | 0%
6.2 | Key Metrics Channel B |  |  |  |  | 0%
6.3 | Performance Evaluation |  |  |  |  | 0%
6.4 | Plan Refinement |  |  |  |  | 0%
7 | Sales Campaigns
7.1 | Campaign A |  |  |  |  | 0%
7.2 | Campaign B |  |  |  |  | 0%
0%
0%
8 | Other
8.1 | Corporate Branding |  |  |  |  | 0%
8.2 | [5 empty] | 0%
0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Event Marketing Gantt
EVENT MARKETING GANTT CHART TEMPLATE
EVENT NAME | [7 empty] | EVENT DATE
MM/DD/YY
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE |  | EVENT DESCRIPTION
MM/DD/YY
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 |  |  | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 |  |  | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 |  |  | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 |  |  | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 |  |  | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 |  |  | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 |  |  | 2026-03-23 | 2026-03-23 | 1 | 50%
2
2.1 |  |  | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 |  |  | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.2.1 | [5 empty] | 0%
3.2.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.3.1 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%
5
5.1 | [5 empty] | 0%
5.2 | [5 empty] | 0%
5.3 | [5 empty] | 0%
5.4 | [5 empty] | 0%
6
6.1 | [5 empty] | 0%
6.2 | [5 empty] | 0%
6.3 | [5 empty] | 0%
6.4 | [5 empty] | 0%
7
7.1 | [5 empty] | 0%
7.2 | [5 empty] | 0%
0%
0%
8
8.1 | [5 empty] | 0%
8.2 | [5 empty] | 0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.