## EXAMPLE - HR Resources Plan
HUMAN RESOURCES PLANNING TEMPLATE EXAMPLE
RESOURCE | NAME | STATUS | START DATE | END DATE | DURATION in days | COMMENTS
Project Manager | Steve C. | Complete | 2022-01-16 | 2022-01-21 | 5
Designer | Claudia K. | In Progress | 2022-01-18 | 2022-01-21 | 3
Quality Assurance | Paul B. | Not Started | 2022-01-22 | 2022-01-23 | 1
Business Analyst | Kevin D. | On Hold | 2022-01-22 | 2022-01-23 | 1
Marketing Manager | Kelly K. | Complete | 2022-01-22 | 2022-01-28 | 6
Software Developer | Ryan H. | Complete | 2022-01-27 | 2022-01-29 | 2
Tester | Maura T. | Complete | 2022-01-28 | 2022-02-04 | 7
Database Administrator | Chantelle C. | Complete | 2022-02-05 | 2022-02-09 | 4
Resource 7 | Staff 7 | Not Started | 2022-01-28 | 2022-02-05 | 8
Resource 8 | Staff 8 | Not Started | 2022-02-04 | 2022-02-06 | 2
Resource 9 | Staff 9 | Not Started | 2022-02-07 | 2022-02-10 | 3
Resource 10 | Staff 10 | Not Started | 2022-02-09 | 2022-02-12 | 3
Resource 11 | Staff 11 | Not Started | 2022-02-11 | 2022-02-14 | 3
Resource 12 | Staff 12 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 13 | Staff 13 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 14 | Staff 14 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 15 | Staff 15 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 16 | Staff 16 | Not Started | 2022-02-15 | 2022-02-17 | 2
Resource 17 | Staff 17 | Not Started | 2022-02-15 | 2022-02-17 | 2
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - HR Resources Planning
HUMAN RESOURCES PLANNING TEMPLATE
RESOURCE | NAME | STATUS | START DATE | END DATE | DURATION in days | COMMENTS
Resource 1 | Name | Complete |  |  | 0
Resource 2 | Name | In Progress |  |  | 0
Resource 3 | Name | Not Started |  |  | 0
|  | On Hold |  |  | 0
|  | Complete |  |  | 0
|  | Complete |  |  | 0
|  | Complete |  |  | 0
|  | Complete |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
|  | Not Started |  |  | 0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options. * Delete any unpopulated rows in your table. *

## Status Keys - DO NOT DELETE
STATUS KEYS - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.