## EXAMPLE Interview Process Gantt
INTERVIEW PROCESS GANTT CHART TEMPLATE EXAMPLE
OPEN POSITION |  |  | INTERVIEW DATE |  | CANDIDATES
Assistant Project Manager |  |  | MM/DD/YY |  | John K. | Robert M. | Maddie T. | Theo S.
PROJECT MANAGER |  |  | TODAY'S DATE |  | Theresa T. | Diana D. | Sara S. | Bert D.
Thomas L. |  |  | MM/DD/YY |  | Name | Name | Name | Name
| TIMELINE |  |  | NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | ASSIGNED TO |  | COMMENTS
PRE-INTERVIEW | 2025-05-05 | 2025-07-01 | 58 | Matthew B. |  | Schedule with recruiting
Identify resource requirements | 2025-05-10 | 2025-08-10 | 93 | Matthew B.
Advertise position to internal and external candidates | 2025-06-10 | 2025-06-15 | 6 | Matthew B. |  | Contact IT for internal e-blast
Assemble candidate applications and resumes | 2025-06-22 | 2025-08-04 | 44 | Matthew B.
CANDIDATE INTERVIEW | 2025-07-14 | 2025-11-01 | 111 | Terri L.
Select candidates to interview | 2025-07-14 | 2026-01-20 | 191 | Terri L.
Conduct interviews | 2025-08-01 | 2025-10-01 | 62 | Terri L.
Second interviews (as required) | 2025-08-14 | 2025-08-30 | 17
CANDIDATE SELECTION | 2025-09-01 | 2025-12-10 | 101
Review final candidates | 2025-10-01 | 2025-11-15 | 46
Conduct final interviews | 2025-10-01 | 2025-12-01 | 62
Contact references | 2025-11-01 | 2025-12-01 | 31
Select best candidate | 2025-11-10 | 2025-12-10 | 31
HIRING
Draft offer letter
Present proespect formal offer
Negotiate compensation
Offer acceptance |  |  | 1
TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Interview Process Gantt
INTERVIEW PROCESS GANTT CHART TEMPLATE
OPEN POSITION |  |  | INTERVIEW DATE |  | CANDIDATES
Title |  |  | MM/DD/YY |  | Name | Name | Name | Name
PROJECT MANAGER |  |  | TODAY'S DATE |  | Name | Name | Name | Name
Name |  |  | MM/DD/YY |  | Name | Name | Name | Name
| TIMELINE |  |  | NOTES
PHASE TITLE | START DATE | END DATE | DURATION in days | ASSIGNED TO |  | COMMENTS
1
1
1
1
1
1
1
1
1
1
1
1
1
1
TIMELINE
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.