## EXAMPLE - Legal Project Mgmt
LEGAL PROJECT MANAGEMENT TEMPLATE
COMPANY NAME |  |  |  | DATE | STATUS | % COMPLETE
Beta Legal Partners |  |  |  | 00/00/0000 | In Progress | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | ESTIMATED WORK | ACTUAL WORK | COMMENTS
Business Incorporation | John K | 2027-09-02 | 2027-09-03 | 2 | Complete | High | 8 | 8
Business Acquisition | Bob C. | 2027-09-03 | 2027-09-07 | 5 | Not Started | Medium | 15 | 12
Liability Defense | Kristin R. | 2027-09-07 | 2027-09-12 | 6 | In Progress | Low | 10 | 8
Patent Application | Donald W. | 2027-09-09 | 2027-09-11 | 3 | Complete | Low | 8 | 8
Task 5 |  | 2027-09-11 | 2027-09-15 | 5 | In Progress | Medium | 25 | 28
Task 6 |  | 2027-09-16 | 2027-09-17 | 2 | Complete | Low | 8 | 8
Task 7 |  | 2027-09-17 | 2027-09-21 | 5 | On Hold | High | 20 | 18.5
Task 8 |  | 2027-09-24 | 2027-10-02 | 9 | Overdue | High | 8 | 8
Task 9 |  | 2027-10-02 | 2027-10-05 | 4 | Complete | Medium | 8 | 8
Task 10 |  | 2027-10-05 | 2027-10-07 | 3 | Not Started | High | 8 | 8
Task 11 |  | 2027-10-06 | 2027-10-09 | 4 | On Hold | Low | 8 | 8
Task 12 |  | 2027-10-10 | 2027-10-10 | 1 | Complete | High | 2.5 | 3
[6 empty] | TOTALS | 128.5 | 125.5
TASK STATUS % |  |  |  | PLANNED VS. ACTUAL COST
STATUS | COUNT | % |  | PLANNED | 237741
Not Started | 2 | 16.67% |  | ACTUAL | 219757
In Progress | 2 | 16.67%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 2 | 16.67%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 5 | 41.67% |  | Actions | 2
Medium | 3 | 25% |  | Change Requests | 4
Low | 4 | 33.33%
TOTAL | 12 | 100%
PROJECT TOTALS
| ESTIMATED | [5 empty] | ACTUAL
PROJECT NAME | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | PROJECT ADMIN | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | PROJECT ADMIN
Project 1 | 7000 | 7000 | 7000 | 12500 | 0 | 18000 | 6650 | 4500 | 3456 | 5678 | 0 | 18000
Project 2 | 2500 | 25000 | 7000 | 13500 | 0 | 19000 | 2540 | 18543 | 3456 | 11344 | 0 | 19000
Project 3 | 3250 | 13546 | 10000 | 14500 | 0 | 32000 | 6500 | 16000 | 12000 | 14789 | 0 | 32000
Project 4 | 1600 | 12345 | 0 | 15500 | 0 | 0 | 2000 | 9876 | 0 | 15000 | 0 | 0
| 0 | 0 | 0 | 16500 | 0 | 0 | 0 | 3425 | 0 | 15000 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 14350 | 57891 | 24000 | 72500 | 0 | 69000 | 17690 | 52344 | 18912 | 61811 | 0 | 69000
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Legal Project Mgmt
LEGAL PROJECT MANAGEMENT TEMPLATE
COMPANY NAME |  |  |  | DATE | STATUS | % COMPLETE
Name |  |  |  | 00/00/0000 | On Hold | 0%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | ESTIMATED WORK | ACTUAL WORK | COMMENTS
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
[6 empty] | TOTALS | 0 | 0
TASK STATUS % |  |  |  | PLANNED VS. ACTUAL COST
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 | 0% |  | ACTUAL | 0
In Progress | 0 | 0%
Complete | 12 | 100%
Overdue | 0 | 0%
On Hold | 0 | 0%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 12 | 100% |  | Actions | 0
Medium | 0 | 0% |  | Change Requests | 0
Low | 0 | 0%
TOTAL | 12 | 100%
PROJECT TOTALS
| ESTIMATED | [5 empty] | ACTUAL
PROJECT NAME | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | PROJECT ADMIN | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | PROJECT ADMIN
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - DO NOT DELETE
Dropdown Keys - DO NOT DELETE
STATUS | PRIORITY
Not Started | High
In Progress | Medium
Complete | Low
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.