## Marketing Gantt Chart - EXAMPLE
MARKETING CAMPAIGN GANTT CHART EXAMPLE
PROJECT TITLE
Project Alpha
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
John K. |  | Weller Corp. |  |  |  | MM/DD/YY
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Establish Goals | Leon W | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 | Determine Target Audience | Kylie R | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 | Develop Creative Concept | Pete S | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 | Identify Marketing Channels | Steve L | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 | Budget and Financial Projection | Allen W | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 | Set up Campaign Calendar | Malik M | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 | Creative Brief | Malik M | 2026-03-23 | 2026-03-23 | 1 | 50%
2 | Creative Development
2.1 | Message Planning | Steve L | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 | Create Marketing Assets | Allen W | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | Gather Customer Testimonials | Malik M |  |  |  | 0%
2.4 | Other | Malik M |  |  |  | 0%
3 | Promotion Plan
3.1 | Email Campaign | Pete S |  |  |  | 0%
3.2 | Social Media | Leon W |  |  |  | 0%
3.2.1 | Sales Outreach | Kylie R |  |  |  | 0%
3.2.2 | Press Release | Kylie R |  |  |  | 0%
3.3 | Print Advertising | Pete S |  |  |  | 0%
3.3.1 | Other | Malik M |  |  |  | 0%
4 | Testing
4.1 | Split Testing | Steve L |  |  |  | 0%
4.2 | Results Analysis | Allen W |  |  |  | 0%
4.3 | Plan Refinement | Malik M |  |  |  | 0%
4.4 | Other | Malik M |  |  |  | 0%
5 | Launch
5.1 | Channel A |  |  |  |  | 0%
5.2 | Channel B |  |  |  |  | 0%
5.3 | Channel C |  |  |  |  | 0%
5.4 | Channel D |  |  |  |  | 0%
6 | Measurement
6.1 | Key Metrics Channel A |  |  |  |  | 0%
6.2 | Key Metrics Channel B |  |  |  |  | 0%
6.3 | Performance Evaluation |  |  |  |  | 0%
6.4 | Plan Refinement |  |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Marketing Gantt Chart
MARKETING CAMPAIGN GANTT CHART
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 |  |  | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 |  |  | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 |  |  | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 |  |  | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 |  |  | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 |  |  | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 |  |  | 2026-03-23 | 2026-03-23 | 1 | 50%
2
2.1 |  |  | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 |  |  | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.2.1 | [5 empty] | 0%
3.2.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.3.1 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%
5
5.1 | [5 empty] | 0%
5.2 | [5 empty] | 0%
5.3 | [5 empty] | 0%
5.4 | [5 empty] | 0%
6
6.1 | [5 empty] | 0%
6.2 | [5 empty] | 0%
6.3 | [5 empty] | 0%
6.4 | [5 empty] | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.