## EXAMPLE - Project Risk Register
PROJECT RISK REGISTER EXAMPLE – BASIC
DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER
44583 | 04/05/20XX | Third party vendor failing to meet service level agreement to build an important component of software | 1 | 8 | 8 | Project team vendor liaison to stay in continual contact with vendor on development of component. Plan established at beginning of project on how component could be developed/accessed on appropriate schedule if vendor does not deliver. | Backup plan has been established; continual communications with vendor; development of component on schedule | Elena Ramirez, project team vendor liaison
44614 | 04/05/20XX | Unclear or misunderstood requirements for software between client and software development team | 2 | 4 | 8 | Software development team will work on detailed plans with client on all expectations for software, and continually revisit the issue throughout the project | Planning documents have been completed, with details on specifications, and team is continually meeting with client representatives | Jeff Petersen – client liaison for development team
44642 | 04/08/20XX | Developer turnover: Losing software developers in important positions, with expected delays in finding and training replacement employees. | 2 | 8 | 16 | Proactive conversations with important members of development team -- at the beginning of and throughout the projects -- about their career plans while the project is ongoing; plan to work on continual mentor training for important positions, so other members of the team can step in and do good work if/when others leave. | Continual conversations with developers and ongoing work on mentor plan and mentor training | Amir Muhammad – lead on project human resources
44673 | 04/12/20XX | Regulatory compliance violations | 1 | 8 | 8 | Sub-group of project team to collect all regulations that applied to previous version of software, and research any new regulations. Create plan on how all requirements will be addressed and included | On track to comply with all regulations | Regulatory compliance sub-team, led by Susan Perkins
|  |  | 1 | 1 | 1
|  |  | 2 | 2 | 4
|  |  | 3 | 4 | 12
|  |  | 4 | 8 | 32
|  |  | 5 | 16 | 80
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Risk Register
PROJECT RISK REGISTER – BASIC
DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5 | PROBABILITY KEY | IMPACT KEY
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5 | 1 | 1
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10 | 2 | 2
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20 | 3 | 4
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40 | 4 | 8
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80 | 5 | 16
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.