## EXAMPLE - Risk Mgmt Heat Map
ENTERPRISE RISK MANAGEMENT HEAT MAP TEMPLATE FOR EXCEL
RISKS BY CATEGORY
After populating your RISK CATEGORIES on the Dropdown Keys tab, enter new data on the BLANK tab.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | RISK CRITERIA | MITIGATION / RESPONSE PLAN | MONITORING FREQUENCY | OWNER | OTHER NOTES
10001 | 00/00/00 | Operational | If there are changes in plans that require additional or different resources, then there will be delays. | 1 | 8 | 8 | Criteria for this risk | A designated team member will continually monitor any proposed changes in plans and ensure communication between teams about proposed changes. | No current issues | Joe Smith; liaison
10002 | 00/00/00 | IT | If contractual issues arise, there will be delays or cost overruns. | 2 | 4 | 8 | Criteria for this risk | The contracts manager will continually monitor contracts, alert the team when there are issues, and ensure that the team addresses and resolves contract issues before they cause delays. |  | Sue Johnson, manager
10003 | 00/00/00 | Financial |  | 2 | 8 | 16 | Criteria for this risk |  | All deadlines currently being monitored | Dale Swenson, manager
10004 | 00/00/00 | Legal/Regulatory |  | 1 | 8 | 8 | Criteria for this risk
|  | Market |  | 1 | 1 | 1 | Criteria for this risk
|  | Credit |  | 1 | 2 | 2
|  | Reputational |  | 1 | 4 | 4
|  | Financial |  | 1 | 8 | 8
|  | Operational |  | 1 | 16 | 16
|  | Credit |  | 2 | 16 | 32
|  | Operational |  | 3 | 16 | 48
|  | Market |  | 4 | 16 | 64
|  | Market |  | 5 | 16 | 80
CLICK HERE TO CREATE IN SMARTSHEET

## Example Data
RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
RISK CATEGORY | – DO NOT ALTER –
Credit | 2
Financial | 2
IT | 1
Legal/Regulatory | 1
Market | 3
Operational | 3
Reputational | 1
PROBABILITY
IMPACT

## BLANK - Risk Mgmt Heat Map
ENTERPRISE RISK MANAGEMENT HEAT MAP TEMPLATE FOR EXCEL
RISKS BY CATEGORY
|  | ENTER RISK CATEGORIES on the Dropdown Keys tab prior to populating chart data. |  | DO NOT ALTER RISK SEVERITY SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | RISK CRITERIA | MITIGATION / RESPONSE PLAN | MONITORING FREQUENCY | OWNER | OTHER NOTES
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
DROPDOWN KEYS DELETE unused rows to remove from RISK COUNT bar chart.
RISK CATEGORY | – DO NOT ALTER –
Credit | 0
Financial | 0
IT | 0
Legal/Regulatory | 0
Market | 0
Operational | 0
Reputational | 0
Other 1 | 0
Other 2 | 0
Other 3 | 0
Other 4 | 0
Other 5 | 0
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.