## EXAMPLE - Risk Register
PROJECT RISK REGISTER EXAMPLE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
10001 | MM/DD/YY | Materials | If there are changes in architectural plans that require additional or different resources, then there will be delays. | 1 | 8 | 8 | The risk is present throughout the process of finalizing architectural plans. | There are changes in the architectural plans. | A designated team member will continually monitor any proposed changes in architectural plans and ensure communication between architectural and construction teams about proposed changes. | No current issues | Joe Smith; architectural liaison
10002 | MM/DD/YY | Contracts | If contractual issues among contractors, subcontractors, or vendors arise, then there will be delays or cost overruns. | 2 | 4 | 8 | The risk is present before most contract work commences. However, the risk will also be present when additional contracts are added in the early phases of construction. | The contracts manager reports any potential contract issues. | The contracts manager will continually monitor contracts, alert the team when there are issues, and ensure that the team addresses and resolves contract issues before they cause delays. | Working on one unresolved issue with the electrician's contract; meeting set for May 2nd | Sue Johnson, contracts manager
10003 | MM/DD/YY | Permits / Regulations | If obtaining appropriate construction permits takes longer than planned, then there will be delays. | 2 | 8 | 16 | The risk is present throughout the construction phase of the project, including when securing required permits at the beginning of construction. | Construction permits do not arrive within the required timeframe. | The construction manager, or another designated team member, will monitor the project schedule and deadlines and ensure that all permits can accommodate the project's construction schedule. | All deadlines currently being monitored | Dale Swenson, construction manager
10004 | MM/DD/YY | Construction Site | If unexpected hazardous waste is found on the property, it will require mitigation or cleanup. | 1 | 8 | 8 | The risk is present throughout the project, especially toward the beginning when conducting site preparation work. | On-site managers report an issue, especially during site preparation. | The construction manager will assign a team member to monitor and explore any possible issues with hazardous waste. | No issues found to this point | Jeff Baker, construction assistant
|  |  |  | 1 | 1 | 1
|  |  |  | 1 | 2 | 2
|  |  |  | 1 | 4 | 4
|  |  |  | 1 | 8 | 8
|  |  |  | 1 | 16 | 16
|  |  |  | 2 | 16 | 32
|  |  |  | 3 | 16 | 48
|  |  |  | 4 | 16 | 64
|  |  |  | 5 | 16 | 80
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Risk Register
PROJECT RISK REGISTER
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Category One
Category Two
Category Three
Category Four
Category Five
Category Six
Category Seven
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.