## EXAMPLE - Project Schedule
SAMPLE PROJECT SCHEDULE TEMPLATE WITH TASK LIST AND GANTT CHART
PROJECT TITLE |  | START DATE | END DATE | DURATION in days | PROJECT MANAGER
Restaurant move to new location |  | 2028-05-03 | 2029-03-29 | 331 | Sean Fontaine
Blank template on next tab.
PROJECT PHASE | KEY PROJECT TASKS | START DATE | END DATE | DURATION in days | ASSIGNED TO | BUDGET & RESOURCES | DELIVERABLES | COMMENTS
CONSTRUCTION | CONSTRUCTION | 2028-05-03 | 2028-09-05 | 126
| Construction in new space | 2028-05-03 | 2028-08-15 | 105 | Construction contractor | link to invoices | All construction completed by 8/15 | Running 1 week behind initial estimates but will still finish before service pause
| Packing and Moving | 2028-08-01 | 2028-09-05 | 36 | Hourly Managers | link to vendor invoices | All equipment set up by 9/05
PREP | PREP | 2028-08-01 | 2028-10-15 | 76
| Finalize new dinner menu | 2028-08-01 | 2028-08-15 | 15 | General Manager | link to project plan
| Back of house training | 2028-08-15 | 2028-09-15 | 32 | General Manager | link to project plan | First reservations for 9/16 | Dinner only
| Front of house training | 2028-09-02 | 2028-09-15 | 14 | General Manager | link to project plan |  | Dinner only
| Finalize brunch menu | 2028-10-01 | 2028-10-15 | 15 | General Manager | link to project plan | Brunch menu due by 10/15
SERVICE | SERVICE | 2028-08-15 | 2029-03-29 | 227
| Service pause | 2028-08-15 | 2028-09-15 | 32 | Chef de Cuisine | link to training plan | Each cook to attend 80 hours of training by 9/15
| Service resumes (Sa-F only) | 2028-09-15 | 2029-03-29 | 196 | General Manager | link to training plan | Each server to attend 40 hours of training by 9/15
| Add Sunday Service | 2028-10-15 | 2029-03-29 | 166 | Executive Chef | link to menu draft and review |  | Staff dinner tasting on 9/10
| Add Brunch | 2028-11-01 | 2029-03-29 | 149 | Executive Chef | link to menu draft and review |  | Staff brunch tasking on 10/25
DELIVERY TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
START DATE = IFERROR(MIN([START DATE, row below]:D9),"")
END DATE = IFERROR(MAX([END DATE, row below]:E9),"")

## BLANK - Project Schedule
PROJECT SCHEDULE TEMPLATE WITH TASK LIST AND GANTT CHART
PROJECT TITLE |  | START DATE | END DATE | DURATION in days | PROJECT MANAGER
User to complete non-shaded cells only.
PROJECT PHASE | KEY PROJECT TASKS | START DATE | END DATE | DURATION in days | ASSIGNED TO | STATUS | BUDGET & RESOURCES | DELIVERABLES | COMMENTS
PHASE 1 | PHASE 1 | 0 | 0
Task #1
Task #2
Task #3
Task #4
Task #5
PHASE 2 | PHASE 2 | 0 | 0
Task #1
Task #2
Task #3
Task #4
Task #5
PHASE 3 | PHASE 3 | 0 | 0
Task #1
Task #2
Task #3
Task #4
Task #5
PHASE 4 | PHASE 4 | 0 | 0
Task #1
Task #2
Task #3
Task #4
Task #5
PHASE 5 | PHASE 5 | 0 | 0
Task #1
Task #2
Task #3
Task #4
Task #5
DELIVERY TIMELINE
Formulas:
START DATE = IFERROR(MIN([START DATE, row below]:D11),"")
END DATE = IFERROR(MAX([END DATE, row below]:E11),"")
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.