## EXAMPLE - Event Marketing Time
EVENT MARKETING TIMELINE TEMPLATE
EVENT
Name
PROJECT MANAGER |  | COMPANY NAME |  |  |  |  | DATE
John K. |  | Weller Corp. |  |  |  |  | MM/DD/YY
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK ID | PROMOTION TYPE | ADDITIONAL INFORMATION | TASK OWNER | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
|  |  |  | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | NATIONAL MARKETING
1.1 | Banner ads |  | Leon W | 2026-03-12 | 2026-03-15 | 4 | 100%
1.1.1 | Determine Target Audience |  | Kylie R | 2026-03-15 | 2026-03-16 | 2 | 100%
1.2 | Develop Creative Concept |  | Pete S | 2026-03-15 | 2026-03-21 | 7 | 90%
1.3 |  |  | Steve L | 2026-03-16 | 2026-03-22 | 7 | 40%
1.4 |  |  | Allen W | 2026-03-17 | 2026-03-22 | 6 | 70%
1.5 |  |  | Malik M | 2026-03-18 | 2026-03-22 | 5 | 60%
1.6 |  |  | Malik M | 2026-03-23 | 2026-03-23 | 1 | 50%
2 | LOCAL MARKETING
2.1 | Message Planning |  | Steve L | 2026-03-24 | 2026-03-28 | 5 | 5%
2.2 | Web ads |  | Allen W | 2026-03-29 | 2026-04-02 | 5 | 30%
2.3 |  |  | Malik M |  |  |  | 0%
2.4 |  |  | Malik M |  |  |  | 0%
3 | PUBLIC RELATIONS
3.1 | Press release |  | Pete S |  |  |  | 0%
3.2 | Webinar |  | Leon W |  |  |  | 0%
3.2.1 |  |  | Kylie R |  |  |  | 0%
3.2.2 |  |  | Kylie R |  |  |  | 0%
3.3 |  |  | Pete S |  |  |  | 0%
3.3.1 |  |  | Malik M |  |  |  | 0%
4 | CONTENT MARKETING
4.1 | Sponsored content |  | Steve L |  |  |  | 0%
4.2 | Landing page |  | Allen W |  |  |  | 0%
4.3 |  |  | Malik M |  |  |  | 0%
4.4 |  |  | Malik M |  |  |  | 0%
5 | SOCIAL MEDIA
5.1 | Twitter | [5 empty] | 0%
5.2 | Facebook | [5 empty] | 0%
5.3 | Instagram | [5 empty] | 0%
5.4 | TikTok | [5 empty] | 0%
6 | ONLINE
6.1 | Website | [5 empty] | 0%
6.2 | Mobile app | [5 empty] | 0%
6.3 | Mobile alerts | [5 empty] | 0%
6.4 | Blog | [5 empty] | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Event Marketing Time
EVENT MARKETING TIMELINE TEMPLATE
EVENT
PROJECT MANAGER |  | COMPANY NAME |  |  |  |  | DATE
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK ID | PROMOTION TYPE | ADDITIONAL INFORMATION | TASK OWNER | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
|  |  |  | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1
1.1.1
1.2
1.3
1.4
1.5
1.6
2
2.1
2.2
2.3
2.4
3
3.1
3.2
3.2.1
3.2.2
3.3
3.3.1
4
4.1
4.2
4.3
4.4
5
5.1
5.2
5.3
5.4
6
6.1
6.2
6.3
6.4

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.