## EXAMPLE - Event Marketing Plan
EVENT MARKETING PLAN TEMPLATE EXAMPLE
|  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
CAMPAIGN TYPE | ADDITIONAL INFO | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
Email Marketing
Pre-launch | bar: PHASE ONE Wk1 to PHASE ONE Wk3
Launch | bar: PHASE TWO Wk5
Early Bird Discount | bar: PHASE TWO Wk6 to PHASE THREE Wk8
Discount Last Chance | bar: PHASE THREE Wk9 to PHASE FOUR Wk10
Last Call to Buy Tickets | bar: PHASE FOUR Wk11
Event Reminders | bar: PHASE TWO Wk6 to PHASE FOUR Wk10
Post Event Updates | bar: PHASE FOUR Wk12
Social Media
Pre-launch | bar: PHASE ONE Wk1 to PHASE ONE Wk3
Webinars
Early Bird Discount | bar: PHASE TWO Wk6 to PHASE THREE Wk8
Discount Last Chance | bar: PHASE THREE Wk9 to PHASE FOUR Wk10
Last Call to Buy Tickets | bar: PHASE FOUR Wk11
Live Event Updates | bar: PHASE FOUR Wk11
Post Event Updates | bar: PHASE FOUR Wk12
Social Media Platforms
Twitter
Facebook | bar: PHASE ONE Wk3 to PHASE FOUR Wk12
Instagram | bar: PHASE TWO Wk4 to PHASE FOUR Wk12
LinkedIn | bar: PHASE TWO Wk4 to PHASE FOUR Wk11
TikTok | bar: PHASE FOUR Wk10 to PHASE FOUR Wk11
Other
Partner Sponsorships
Create Program | bar: PHASE ONE Wk1
Secure Sponsorships | bar: PHASE ONE Wk2
Finalize Sponsorships | bar: PHASE ONE Wk3
Local Marketing
Web Ads | bar: PHASE ONE Wk3 to PHASE FOUR Wk11
News/Media | bar: PHASE THREE Wk7 to PHASE FOUR Wk11
National Marketing
Banner Ads | bar: PHASE TWO Wk4 to PHASE FOUR Wk11
Web
Development | bar: PHASE ONE Wk1 to PHASE ONE Wk3
Website | bar: PHASE ONE Wk3 to PHASE TWO Wk5; PHASE THREE Wk7 to PHASE FOUR Wk11
Mobile App | bar: PHASE TWO Wk4 to PHASE FOUR Wk11
Mobile Alerts | bar: PHASE TWO Wk6 to PHASE FOUR Wk11
Pay-Per-Click | bar: PHASE TWO Wk6 to PHASE FOUR Wk10
SEO | bar: PHASE TWO Wk4 to PHASE THREE Wk9
Market Research
Surveys | bar: PHASE FOUR Wk12
Campaigns
Campaign A | bar: PHASE ONE Wk1 to PHASE ONE Wk3
Campaign B | bar: PHASE TWO Wk4 to PHASE TWO Wk6
Campaign C | bar: PHASE TWO Wk6 to PHASE THREE Wk8
Campaign D | bar: PHASE THREE Wk8 to PHASE FOUR Wk10
Campaign E | bar: PHASE FOUR Wk11
Other
Branding | bar: PHASE ONE Wk1 to PHASE TWO Wk4
Post-Event Outreach | bar: PHASE ONE Wk1 to PHASE TWO Wk4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Event Marketing Plan
EVENT MARKETING PLAN TEMPLATE
|  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
CAMPAIGN TYPE | ADDITIONAL INFO | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Campaign Type
Other

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.