## EXAMPLE Project Schedule Gantt
PROJECT SCHEDULE TEMPLATE WITH GANTT CHART EXAMPLE
PROJECT NAME |  |  |  | START DATE
Project Alpha |  |  |  | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
PROJECT MANAGER |  |  |  | END DATE |  |  | OVERALL PROGRESS
Raghu Prakash |  |  |  | MM/DD/YY |  |  | 20%
PROJECT DELIVERABLE Description of project deliverable
|  | TASKS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | TASK TITLES | OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | time axis 2025-03-31 to 2025-08-15
In Progress | HIGH | PROJECT KICKOFF |  | 2025-03-31 | 2025-04-21 | 16 |  | 74.33% | bar: 2025-03-31 to 2025-08-15
Not Started | MED | Schedule kickoff meeting | Brent W. | 2025-03-31 | 2025-04-03 | 4 |  | 33% | bar: 2025-03-31 to 2025-04-03
Complete | MED | Agree on objectives | June T. | 2025-04-02 | 2025-04-18 | 13 |  | 100% | bar: 2025-04-02 to 2025-04-18
In Progress | LOW | P1 Task 3 | June T. | 2025-04-13 | 2025-04-18 | 5 |  | 90% | bar: 2025-04-14 to 2025-04-18
In Progress | LOW | P1 Task 4 |  | 2025-04-03 | 2025-04-12 | 7 |  | 33% | bar: 2025-04-03 to 2025-04-11
On Hold | LOW | P1 Task 5 |  | 2025-04-09 | 2025-04-20 | 8 |  | 100% | bar: 2025-04-09 to 2025-04-18
Needs Review | LOW | P1 Task 6 |  | 2025-04-18 | 2025-04-21 | 2 |  | 90% | bar: 2025-04-18 to 2025-04-21
Needs Update | HIGH | INITIATION |  | 2025-04-22 | 2025-06-23 | 45 |  | 25% | bar: 2025-03-31 to 2025-08-15
Needs Update | MED | Detail requests | June T. | 2025-04-22 | 2025-06-21 | 44 |  | 70% | bar: 2025-04-22 to 2025-06-20
In Progress | MED | Hardware requests | Kirk C. | 2025-04-30 | 2025-05-02 | 3 |  | 60% | bar: 2025-04-30 to 2025-05-02
In Progress | MED | Final resources plan | Jason D. | 2025-05-05 | 2025-06-19 | 34 |  | 20% | bar: 2025-05-05 to 2025-06-19
In Progress | MED | Staffing | Seo F. | 2025-05-06 | 2025-06-03 | 21 |  | 0% | bar: 2025-05-06 to 2025-06-03
In Progress | MED | P2 Task 5 |  |  |  | 0 |  | 0%
In Progress | MED | P2 Task 6 |  |  |  | 0 |  | 0%
In Progress | HIGH | DEVELOPMENT |  | 2025-04-14 | 2025-04-25 | 10 |  | 74.33% | bar: 2025-03-31 to 2025-08-15
In Progress | HIGH | Technical requests | Luiza L. | 2025-04-14 | 2025-04-18 | 5 |  | 33% | bar: 2025-04-14 to 2025-04-18
In Progress | HIGH | DB development | Raghu P. | 2025-04-15 | 2025-04-16 | 2 |  | 100% | bar: 2025-04-15 to 2025-04-16
In Progress | HIGH | API development | Raghu P. | 2025-04-17 | 2025-04-17 | 1 |  | 90% | bar: 2025-04-17
In Progress | HIGH | P3 Task 4 |  | 2025-04-21 | 2025-04-24 | 4 |  | 33% | bar: 2025-04-21 to 2025-04-24
In Progress | HIGH | P3 Task 5 |  | 2025-04-22 | 2025-04-23 | 2 |  | 100% | bar: 2025-04-22 to 2025-04-23
In Progress | HIGH | P3 Task 6 |  | 2025-04-25 | 2025-04-25 | 1 |  | 90% | bar: 2025-04-25
In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  | 0 | 0 | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
In Progress | HIGH |  |  |  |  | 0 |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
END DATE = MIN([END DATE, row below]:F18)
END DATE = MIN(IF([END DATE, row below]:F32="","",[END DATE, row below]:F32))

## BLANK Project Schedule Gantt
PROJECT SCHEDULE TEMPLATE WITH GANTT CHART
PROJECT NAME |  |  |  | START DATE
|  |  |  | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
PROJECT MANAGER |  |  |  | END DATE |  |  | OVERALL PROGRESS
|  |  |  | MM/DD/YY |  |  | 20%
PROJECT DELIVERABLE Description of project deliverable
|  | TASKS |  |  |  |  | DELIVERABLES |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | TASK TITLES | OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | time axis 2025-03-31 to 2025-08-15
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%
[6 empty] | 0 |  | 0%

## Dropdown keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
STATUS | PRIORITY
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.