## EX - Project Transition Plan
PROJECT TRANSITION PLAN TEMPLATE
PROJECT TITLE |  | PLAN CREATED BY |  | DATE
Department Merger |  | Barbara Kenzie |  | 02/02/20XX
GOALS
Merge Sales and Marketing Departments
RISKS
1. Cultural differences between departments 2. Loss of focus 3. Resistance to change 4. Overlapping responsibilities 5. Integration challenges 6. Loss of specialized skills
ASSUMPTIONS
1. Common goals 2. Customer focus engaging with potential customers at scale 3. Data-driven approach 4. Collaboration 5. Integration challenges 6. Resistance to change
OTHER
TASK / ASSIGNMENT
TRANSITION ROLE | ASSIGNED TO | START DATE | END DATE | NOTES
Transition Team Leader | Kate Ester | 03/01/20XX | 05/25/20XX
Project Leader | Alexander Josef | 03/01/20XX | TBD
Transition Specialist | Hayden Maripol | 03/01/20XX | TBD
Project Team | Pranab Kumar
Database Administrator | Eva French
Systems and Networking | Robert Harris | 04/01/20XX | 05/25/20XX | Outside consultant
Production Support | Yasen Vernon
Desktop Support | Hanifa Khell
Help Desk | Hanifa Khell
OPS | David Adams
Platform Support | Eva French |  |  | May delegate to Help Desk team.
Project Development | Mark Seeley
TASKS | ASSIGNED TO | START DATE | END DATE | NOTES
Coordinate transition planning meeting | Kate Ester | 03/01/20XX | 03/02/20XX
Distribute project initiation plan or project plan | Alexander Josef
Attend transition planning | All Team Leaders | TBD | TBD | Per Kate Ester 03/02/20XX
Identify project activities to be completed before transition can start | Alexander Josef | 03/01/20XX | 03/10/20XX
Conduct skill gap analysis | Hayden Maripol | 03/15/20XX | 03/20/20XX
TRAINING | ASSIGNED TO | START DATE | END DATE | NOTES
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Transition Plan
PROJECT TRANSITION PLAN TEMPLATE
PROJECT TITLE |  | PLAN CREATED BY |  | DATE
GOALS
RISKS
ASSUMPTIONS
OTHER
TASK / ASSIGNMENT
TRANSITION ROLE | ASSIGNED TO | START DATE | END DATE | NOTES
TASKS | ASSIGNED TO | START DATE | END DATE | NOTES
TRAINING | ASSIGNED TO | START DATE | END DATE | NOTES

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.