**** **PROJECT TRANSITION PLAN**

|  |  |  |
| --- | --- | --- |
| PROJECT TITLE | PLAN CREATED BY | DATE |
| Department Merger | Barbara Kenzie | 02/02/20XX |

|  |
| --- |
| GOALS |
| Merge Sales and Marketing Departments |

|  |
| --- |
| RISKS |
| 1. Cultural differences between departments2. Loss of focus3. Resistance to change4. Overlapping responsibilities5. Integration challenges6. Loss of specialized skills  |

|  |
| --- |
| ASSUMPTIONS |
| 1. Common goals2. Customer focus engaging with potential customers at scale3. Data-driven approach4. Collaboration5. Integration challenges6. Resistance to change  |

|  |
| --- |
| OTHER |
|  |

|  |
| --- |
| TASK / ASSIGNMENT |
| TRANSITION ROLE | ASSIGNED TO | START DATE | END DATE | NOTES |
| Transition Team Leader | Kate Ester | 03/01/20XX | 05/25/20XX |   |
| Project Leader | Alexander Josef | 03/01/20XX | TBD |   |
| Transition Specialist | Hayden Maripol | 03/01/20XX | TBD |   |
| Project Team | Pranab Kumar |   |   |   |
| Database Administrator | Eva French |   |   |   |
| Systems and Networking | Robert Harris | 04/01/20XX | 05/25/20XX | Outside consultant |
| Production Support | Yasen Vernon |   |   |   |
| Desktop Support | Hanifa Khell |   |   |   |
| Help Desk | Hanifa Khell |   |   |   |
| OPS | David Adams |   |   |   |
| Platform Support | Eva French |   |   | May delegate to Help Desk team. |
| Project Development | Mark Seeley |   |   |   |
| TASKS | ASSIGNED TO | START DATE | END DATE | NOTES |
| Coordinate transition planning meeting | Kate Ester | 03/01/20XX | 03/02/20XX |   |
| Distribute project initiation plan or project plan | Alexander Josef |   |   |   |
| Attend transition planning | All Team Leaders | TBD | TBD | Per Kate Ester 03/02/20XX |
| Identify project activities to be completed before transition can start | Alexander Josef | 03/01/20XX | 03/10/20XX |   |
| Conduct skill gap analysis | Hayden Maripol | 03/15/20XX | 03/20/20XX |   |
| TRAINING | ASSIGNED TO | START DATE | END DATE | NOTES |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |
|   |   |   |   |   |

|  |
| --- |
| **DISCLAIMER**Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |