## Example - Business Action Plan
BUSINESS ACTION PLAN TEMPLATE EXAMPLE
PROJECT MANAGER |  |  | TODAY'S DATE
Brent Williams |  |  | MM/DD/YY
GOAL
Write your goal statement below.
ACTION PLAN
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | HAZARD FORECAST | OUTCOME
Goal #1: Select Venue |  | Medium | Complete
Identify venue options | Sally J. | High | Complete | 2022-09-30 | 2022-10-02
Visit venues | Sally J. | Medium | On Hold | 2022-10-05 | 2022-10-09 | Find staff to attend site visit
Sign contract | Maria S. | Low | In Progress | 2022-10-12 | 2022-10-12 | Attorney / Legal Dept.
|  | Low | Complete
Goal #2: Secure Speakers |  | High | In Progress
Recruit speakers | Sally J. | Medium | In Progress | 2022-10-07 | 2022-10-12
Speaker bios | Sally J. | Medium | In Progress | 2022-10-12 | 2022-10-14
Create and send speaker packets | Maria S. | Low | Complete | 2022-10-13 | 2022-10-16
Confirm speakers | Sally J. | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
Goal #3: Recruit Sponsors |  | Low | In Progress
Identify sponsors | John S. | Low | In Progress | 2022-10-13 | 2022-10-19 | Fundraising and Web team
Write up sponsor agreement | Maria S. | Low | In Progress | 2022-10-15 | 2022-10-16
Send emails | John S. | Low | Not Started | 2022-10-19 | 2022-10-21
Make cold calls | John S. | Low | Not Started | 2022-10-21 | 2022-10-23 | From sales team
|  | Low | On Hold
Goal #4: Promote event |  | High | Complete |  |  | Marketing team
Create banners | Morgan K. | High | Complete | 2022-10-26 | 2022-10-28
Order swag | Morgan K. | High | Complete | 2022-10-28 | 2022-10-28 | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | High | Complete | 2022-10-13 | 2022-10-26
Make marketing materials | Karen Z. | High | Complete | 2022-10-26 | 2022-10-30
|  | High | Complete
CLICK HERE TO CREATE IN SMARTSHEET

## Blank - Business Action Plan
BUSINESS ACTION PLAN TEMPLATE EXAMPLE
PROJECT MANAGER |  |  | TODAY'S DATE
Name |  |  | MM/DD/YY
GOAL
Write your goal statement below.
ACTION PLAN
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | HAZARD FORECAST | OUTCOME
Goal #1: |  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
Goal #2: |  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
Goal #3: |  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
Goal #4: |  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress
|  | Low | In Progress

## Dropdown Key - Do Not Delete
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.