## Example - Project Action Plan
PROJECT ACTION PLAN TEMPLATE EXAMPLE
PROJECT NAME
Project Beta
PROJECT MANAGER |  |  | TODAY'S DATE
Brent Williams |  |  | MM/DD/YY
GOAL 1
Statement/description for Goal 1
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Project Conception and Initiation | Ira M. | Medium | Complete | 2022-09-30 | 2022-09-30
Project Charter | Sally J. | High | Complete | 2022-10-01 | 2022-10-01
Charter Revisions | Sally J. | Medium | On Hold | 2022-10-02 | 2022-10-02
Research | Maria S. | Low | In Progress | 2022-10-03 | 2022-10-03
Projections | Ira M. | Low | Complete | 2022-10-04 | 2022-10-04
Stakeholders | Ira M. | High | In Progress | 2022-10-05 | 2022-10-05
Guidelines | Sally J. | Medium | In Progress | 2022-10-06 | 2022-10-06
Project Initiation | Sally J. | Medium | In Progress | 2022-10-07 | 2022-10-07
| Maria S. | Low | Complete | 2022-10-08 | 2022-10-08
| Sally J. | Medium | On Hold | 2022-10-09 | 2022-10-09
|  | Low | In Progress | 2022-10-10 | 2022-10-10
GOAL 2
Statement/description for Goal 2
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Project Definition and Planning | Ira M. | Medium | Complete | 2022-09-30 | 2022-09-30
Scope and Goal Setting | Sally J. | High | Complete | 2022-09-30 | 2022-10-02
Budget | Sally J. | Medium | On Hold | 2022-10-05 | 2022-10-09
Communication Plan | Maria S. | Low | In Progress | 2022-10-12 | 2022-10-12
Risk Management | John K. | Low | Complete
|  | High | In Progress
|  | Medium | In Progress | 2022-10-07 | 2022-10-12
|  | Medium | In Progress | 2022-10-12 | 2022-10-14
|  | Low | Complete | 2022-10-13 | 2022-10-16
|  | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
GOAL 3
Statement/description for Goal 3
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Project Launch and Execution | John K. | Medium | Complete | 2022-09-30 | 2022-09-30
Status and Tracking | Sally J. | High | Complete | 2022-09-30 | 2022-10-02
KPIs | Sally J. | Medium | On Hold | 2022-10-05 | 2022-10-09
Monitoring | Maria S. | Low | In Progress | 2022-10-12 | 2022-10-12
Forecasts | Donald W. | Low | Complete
Project Updates | Donald W. | High | In Progress
Chart Updates | Sally J. | Medium | In Progress | 2022-10-07 | 2022-10-12
|  | Medium | In Progress | 2022-10-12 | 2022-10-14
|  | Low | Complete | 2022-10-13 | 2022-10-16
|  | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
GOAL 4
Statement/description for Goal 4
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Project Performance / Monitoring | Sally J. | Medium | Complete | 2022-09-30 | 2022-09-30
Project Charter | Sally J. | High | Complete | 2022-09-30 | 2022-10-02
Charter Revisions | Sally J. | Medium | On Hold | 2022-10-05 | 2022-10-09
Research | Maria S. | Low | In Progress | 2022-10-12 | 2022-10-12
Projections | Maria S. | Low | Complete
Stakeholders | Maria S. | High | In Progress
Guidelines | Sally J. | Medium | In Progress | 2022-10-07 | 2022-10-12
Project Initiation | Sally J. | Medium | In Progress | 2022-10-12 | 2022-10-14
|  | Low | Complete | 2022-10-13 | 2022-10-16
|  | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
GOAL 5
Statement/description for Goal 5
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Project Lessons Learned | Ira M. | Medium | Complete | 2022-09-30 | 2022-09-30
Review |  | High | Complete | 2022-09-30 | 2022-10-02
|  | Medium | On Hold | 2022-10-05 | 2022-10-09
|  | Low | In Progress | 2022-10-12 | 2022-10-12
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress | 2022-10-07 | 2022-10-12
|  | Medium | In Progress | 2022-10-12 | 2022-10-14
|  | Low | Complete | 2022-10-13 | 2022-10-16
|  | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
CLICK HERE TO CREATE IN SMARTSHEET

## Blank - Project Action Plan
PROJECT ACTION PLAN TEMPLATE
PROJECT NAME
Name
PROJECT MANAGER |  |  | TODAY'S DATE
Name |  |  | MM/DD/YY
GOAL 1
Statement/description for Goal 1
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Action description | Name | Medium | Complete | MM/DD | MM/DD
Description |  | High | Complete
|  | Medium | On Hold
|  | Low | In Progress
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress
|  | Medium | In Progress
|  | Low | Complete
|  | Medium | On Hold
|  | Low | In Progress
GOAL 2
Statement/description for Goal 2
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
Action description | Name | Medium | Complete
Description |  | High | Complete
|  | Medium | On Hold
|  | Low | In Progress
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress
|  | Medium | In Progress
|  | Low | Complete
|  | Medium | On Hold
|  | Low | In Progress
GOAL 3
Statement/description for Goal 3
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
|  | Medium | Complete
|  | High | Complete
|  | Medium | On Hold
|  | Low | In Progress
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress
|  | Medium | In Progress
|  | Low | Complete
|  | Medium | On Hold
|  | Low | In Progress
GOAL 4
Statement/description for Goal 4
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
|  | Medium | Complete
|  | High | Complete
|  | Medium | On Hold
|  | Low | In Progress
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress
|  | Medium | In Progress
|  | Low | Complete
|  | Medium | On Hold
|  | Low | In Progress
GOAL 5
Statement/description for Goal 5
ACTION DESCRIPTION | RESPONSIBLE | PRIORITY | STATUS | START | END | RESOURCES REQUIRED | DESIRED OUTCOME | NOTES
|  | Medium | Complete
|  | High | Complete
|  | Medium | On Hold
|  | Low | In Progress
|  | Low | Complete
|  | High | In Progress
|  | Medium | In Progress
|  | Medium | In Progress
|  | Low | Complete
|  | Medium | On Hold
|  | Low | In Progress

## Dropdown Key - Do Not Delete
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.