## SAMPLE - RAID Log
RAID TEMPLATE – EXAMPLE
ID No. | Item Description | RAID Category | Impact Description | Urgency | Item Raised By | Date Raised | Date Checked | Mitigation Notes | Owner
–– | Give a brief summary of the risk. | Risk, Assumption, Issue, Dependency | What will happen if the risk is not mitigated or eliminated? | Low, Moderate, High, Critical | Who identified this issue? | When was this identified? | When was this verified? | What can be done to lower or eliminate the impact or probability? | Who's responsible?
101 | Material delivery is delayed | Risk | Production stops | Low | Leigh Gibbs | 05/07/XX | 05/11/XX |  | Marta Hicks
102 | Machinery breakdowns | Assumption | Production delayed | High | Mathias Nevin | 05/12/XX | 05/12/XX |  | Mateus Tobin
103 | Part on backorder | Issue | Production stalled | Critical
104 | Paint must cure before packaging | Dependency | Production delayed | Moderate
105
106
107
108
109
110
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - RAID Log
RAID TEMPLATE
ID No. | Item Description | RAID Category | Impact Description | Urgency | Item Raised By | Date Raised | Date Checked | Mitigation Notes | Owner
–– | Give a brief summary of the risk. | Risk, Assumption, Issue, Dependency | What will happen if the risk is not mitigated or eliminated? | Low, Moderate, High, Critical | Who identified this issue? | When was this identified? | When was this verified? | What can be done to lower or eliminate the impact or probability? | Who's responsible?

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
RAID Category | Impact
Risk | Low
Assumption | Moderate
Issue | High
Dependency | Critical

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.