## EXAMPLE - Ad Campaign Timeline
ADVERTISING CAMPAIGN TIMELINE TEMPLATE EXAMPLE
AT RISK | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Planning | Complete | Pietro A. | 2024-01-02 | 2024-01-08 | 6
| Establish goals | Not Started | Pietro A. | 2024-01-04 | 2024-01-11 | 7 | Contact Marketing Director
| Determine target audience | Not Started | Pietro A. | 2024-01-07 | 2024-01-11 | 4
| Creative Development | Complete | Morgan V. | 2024-01-10 | 2024-01-15 | 5
| Message planning | On Hold | Morgan V. | 2024-01-13 | 2024-01-20 | 7
| Promotional Plan | On Hold | Morgan V. | 2024-01-16 | 2024-01-29 | 13 | Send draft prior to team meeting
| Email campaign | On Hold | Aila K. | 2024-01-19 | 2024-02-01 | 13
| Social media | In Progress | Aila K. | 2024-01-22 | 2024-02-09 | 18
| Testing | In Progress | Gordana S. | 2024-01-25 | 2024-02-05 | 11
| Split testing | In Progress | Morgan V. | 2024-01-28 | 2024-02-06 | 9
| Results analysis | In Progress | Gordana S. | 2024-01-31 | 2024-02-02 | 2
| Plan refinement | In Progress | Pietro A. | 2024-02-04 | 2024-02-12 | 8
| Other | In Progress |  | 2024-02-06 | 2024-02-14 | 8
| Measurement | In Progress |  | 2024-02-09 | 2024-02-17 | 8
| Subtask1 | In Progress |  | 2024-02-18 | 2024-02-20 | 2
|  | In Progress |  | 2024-02-15 | 2024-02-23 | 8
|  | In Progress |  | 2024-02-18 | 2024-02-26 | 8
|  | In Progress |  | 2024-02-21 | 2024-02-29 | 8
|  | In Progress |  | 2024-02-24 | 2024-03-03 | 8
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Ad Campaign Timeline
ADVERTISING CAMPAIGN TIMELINE TEMPLATE
AT RISK | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Task 1 | Not Started | Name |  |  | 0
| Subtask 1.1 | Not Started |  |  |  | 0
| Subtask 1.2 | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
| Task 2 | Not Started |  |  |  | 0
| Subtask 2.1 | Not Started |  |  |  | 0
| Subtask 2.2 | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
|  | Not Started |  |  |  | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.