## BLANK - Project Milestone Chart
FUNDRAISING CAMPAIGN PROJECT MILESTONE TEMPLATE
DATE | MILESTONE | PLACEMENT HEIGHT and DIRECTION | ASSIGNEE | STATUS | COMMENTS
5
-5
10
-10
15
-15
10
-10
5
-5
5
CLICK HERE TO CREATE IN SMARTSHEET
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## EX - Project Milestone Chart
FUNDRAISING CAMPAIGN PROJECT MILESTONE TEMPLATE – EXAMPLE
DATE | MILESTONE | PLACEMENT HEIGHT and DIRECTION | ASSIGNEE | STATUS | COMMENTS
2030-01-16 | Project needs assessment approval | 5 | Morgan Jones | Complete | Stakeholders have signed off
2030-01-18 | Key case messages outlined | -5 | Sue Matthews | Complete | Reviewed and approved by fundraising team & stakeholders
2030-01-22 | Non-philanthropic revenue options identified | 10 | Morgan Jones | In Progress | More potential sources under research
2030-01-27 | Financing options identified | -10 | Phil Rogers | On Hold | More research required
2030-01-28 | Top lead donor identification | 15 | Morgan Jones | In Progress | Networking
2030-01-31 | How much money can be raised / goal | -15 | Lou Smith | In Progress | Readjusting budget
2030-02-01 | Project scope adjustment | 10 | Lou Smith | Not Started | Pending donor identification
2030-02-04 | Messaging refinement | -10 | Sue Matthews | Not Started | Messaging pending input from donors and board
2030-02-09 | Board campaign gifts secured | 15 | Morgan Jones | Not Started | Pending pledges
2030-02-11 | Marketing and donor acquisition in place and running | -15 | Lou Smith | Not Started | Pending scope, messaging, donor lists
2030-02-15 | Project complete | 5 | Team | Not Started | Ribbon cutting and opening at completion

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.