## EXAMPLE Project Status Minutes
PROJECT STATUS MEETING MINUTES TEMPLATE
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
MM/DD/YY | Conference Room B |  | 12:00 | 14:00
ATTENDEES
NAME |  | ROLE
Carmen Robertson |  | Project Manager
Hasaon Bocker |  | Team Lead
Denis Vidal |  | Financial Analyst
Jose Price |  | Developer
2. PROJECT OVERVIEW
A brief overview of the project's goals and objectives. Include a summary of the project's current status.
OVERVIEW
Project Beta overview and goals. Summary of Project Beta's status.
3. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review of Previous Meeting |  | Carmen | 12:05
Status Updates |  | Carmen | 12:10
Discussion of Project Budget |  | Denis | 12:20
New Feature Development |  | Jose
Action Items and Next Steps |  | Carmen
Risk Management |  | Carmen
Other Business |  | Carmen
Upcoming Milestones |  | Jose
Meeting Conclusion and Next Meeting Date |  | Carmen
4. PREVIOUS ACTION ITEMS REVIEW
A summary of action items from the previous meeting. Include status updates on the completion of these action items.
SUMMARY
Reviewed minutes from the last meeting held on September 7.
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
Item 1 - Prototype approval received |  | Carmen | Complete
Item 2 - Backend development nearing completion |  | Jose | In Progress
Carmen discussed the current project timeline, noting that frontend design is ahead of schedule. |  | Carmen | In Progress
Jose shared progress on the backend development, mentioning challenges with integrating external APIs. |  | Jose | In Progress
Review of UI mockups, highlighting changes based on client feedback. |  | Jose | In Progress
5. MILESTONE PROGRESS
Updates on the completion of key milestones or phases, including any delays or challenges encountered.
MILESTONES
Completion of Development Phase - MM/DD/YY
Marketing Campaign - MM/DD/YY
6. TASK AND ACTIVITY UPDATES
Updates on the progress of specific tasks and activities, including any tasks that are completed, in progress, or delayed.
TASKS AND ACTIVITIES |  | OWNER | STATUS
Finalize UI mockups and share with team |  | Jose | Complete
Conduct thorough testing of software |  | Carmen | Delayed
In Progress
In Progress
In Progress
7. ISSUES AND RISKS
Discuss any new risks or issues identified during the meeting. Include mitigation strategies.
RISK OR ISSUE |  | MITIGATION STRATEGY
Identified a potential security vulnerability in the external API integration. |  | Perform a security audit and recommend mitigation strategies.
8. RESOURCE ALLOCATION
Discuss resource allocation and availability. Include any resource constraints or adjustments.
RESOURCES |  | AVAILABILITY | CONSTRAINTS
9. BUDGET AND FINANCIAL UPDATES
Updates on the project expenditures and budget status. Include any deviations from the original budget plan
BUDGET ITEM | BUDGETED AMOUNT | ACTUAL AMOUNT | NOTES
Item A | 2500 | 1500
Item B | 1200 | 1324.5
Item C | 1234 | 950
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
10. CLIENT / STAKEHOLDER COMMUNICATION
Note discussions of any recent interactions with clients or stakeholders. Include updates on feedback received or any changes requested.
CLIENT / STAKEHOLDER |  | DISCUSSION NOTES
Client Alpha |  | Decision: Allocate an additional budget of $10,000 for marketing efforts.
Client Beta |  | Update: New feature development
Client Omega |  | Decision: Proceed with the new feature development, with weekly progress reviews.
11. UPCOMING TASKS AND MILESTONES
List tasks and milestones expected to be completed before the next meeting. Include potential challenges or concerns regarding upcoming work.
TASKS AND MILESTONES
Completion of Development Phase
Marketing Campaign
12. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
Confirm development completion by September 30, for QA testing.
Begin marketing campaign by October 5, targeting potential users.
13. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
Meeting concluded with a summary of discussions and action items.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
MM/DD/YY | Conference Room A
14. ATTACHMENTS OR SUPPORTING MATERIALS
Link or attach relevant documents, presentations, or reports discussed during the meeting.
MATERIALS
Links
15. APPROVAL AND SIGNATURES
Sign below to approve meeting minutes.
PARTICIPANT NAME |  | SIGNATURE
Name
Name
Name
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Status Minutes
PROJECT STATUS MEETING MINUTES TEMPLATE
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
MM/DD/YY
ATTENDEES
NAME |  | ROLE
2. PROJECT OVERVIEW
A brief overview of the project's goals and objectives. Include a summary of the project's current status.
OVERVIEW
3. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
4. PREVIOUS ACTION ITEMS REVIEW
A summary of action items from the previous meeting. Include status updates on the completion of these action items.
SUMMARY
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
5. MILESTONE PROGRESS
Updates on the completion of key milestones or phases, including any delays or challenges encountered.
MILESTONES
6. TASK AND ACTIVITY UPDATES
Updates on the progress of specific tasks and activities, including any tasks that are completed, in progress, or delayed.
TASKS AND ACTIVITIES |  | OWNER | STATUS
7. ISSUES AND RISKS
Discuss any new risks or issues identified during the meeting. Include mitigation strategies.
RISK OR ISSUE |  | MITIGATION STRATEGY
8. RESOURCE ALLOCATION
Discuss resource allocation and availability. Include any resource constraints or adjustments.
RESOURCES |  | AVAILABILITY | CONSTRAINTS
9. BUDGET AND FINANCIAL UPDATES
Updates on the project expenditures and budget status. Include any deviations from the original budget plan
BUDGET ITEM | BUDGETED AMOUNT | ACTUAL AMOUNT | NOTES
10. CLIENT / STAKEHOLDER COMMUNICATION
Note discussions of any recent interactions with clients or stakeholders. Include updates on feedback received or any changes requested.
CLIENT / STAKEHOLDER |  | DISCUSSION NOTES
11. UPCOMING TASKS AND MILESTONES
List tasks and milestones expected to be completed before the next meeting. Include potential challenges or concerns regarding upcoming work.
TASKS AND MILESTONES
12. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
13. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
MM/DD/YY
14. ATTACHMENTS OR SUPPORTING MATERIALS
Link or attach relevant documents, presentations, or reports discussed during the meeting.
MATERIALS
Links
15. APPROVAL AND SIGNATURES
Sign below to approve meeting minutes.
PARTICIPANT NAME |  | SIGNATURE
Name
Name
Name

## – Disclaimer –
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.