## EXAMPLE Project Team Minutes
PROJECT TEAM MEETING MINUTES TEMPLATE
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
MM/DD/YY | Conference Room B |  | 12:00 | 14:00
ATTENDEES
NAME |  | ROLE
Carmen Robertson |  | Project Manager
Hasaon Bocker |  | Team Lead
Denis Vidal |  | Financial Analyst
Jose Price |  | Developer
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review of Previous Meeting |  | Carmen | 12:05
Status Updates |  | Carmen | 12:10
Discussion of Project Budget |  | Denis | 12:20
New Feature Development |  | Jose
Action Items and Next Steps |  | Carmen
Risk Management |  | Carmen
Other Business |  | Carmen
Upcoming Milestones |  | Jose
Meeting Conclusion and Next Meeting Date |  | Carmen
3. PREVIOUS MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on the completion of these action items.
SUMMARY
Reviewed minutes from the last meeting held on September 7.
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
Item 1 - Prototype approval received |  | Carmen | Complete
Item 2 - Backend development nearing completion |  | Jose | In Progress
Carmen discussed the current project timeline, noting that frontend design is ahead of schedule. |  | Carmen | In Progress
Jose shared progress on the backend development, mentioning challenges with integrating external APIs. |  | Jose | In Progress
Review of UI mockups, highlighting changes based on client feedback. |  | Jose | In Progress
4. DISCUSSION POINTS
Include a detailed discussion of each agenda item. Include key points, decisions, and information shared during the discussion. Include any presentations or visuals shared during the meeting.
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Denis presented the latest budget report, noting that development costs are within projections.
Team discussed potential marketing expenses for the upcoming launch. |  | Decision: Allocate an additional budget of $10,000 for marketing efforts.
Jose presented a detailed plan for the new feature implementation. |  | New feature development
Discussion focused on technical feasibility and potential user impact. |  | Decision: Proceed with the new feature development, with weekly progress reviews.
5. ACTION ITEMS
List action items and identified during the meeting. Include responsible parties assigned to each item, due dates for each item, and note action items carried forward from previous meetings.
ACTION ITEM |  | OWNER | DUE DATE
Item 3 - Finalize UI mockups and share with team |  | Jose | MM/DD/YY
Item 4 - Conduct thorough testing of software |  | Carmen | MM/DD/YY
6. DECISIONS MADE
Include a clear and concise description of decisions reached during the meeting. Include justifications or context for the decisions, if necessary.
DECISIONS
Approve the marketing budget increase based on projected ROI - Justification: Increased marketing efforts are essential for a successful product launch.
7. RISKS AND ISSUES
Discuss any new risks or issues identified during the meeting. Include mitigation strategies.
RISK OR ISSUE |  | MITIGATION STRATEGY
Identified a potential security vulnerability in the external API integration. |  | Perform a security audit and recommend mitigation strategies.
8. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
Confirm development completion by September 30, for QA testing.
Begin marketing campaign by October 5, targeting potential users.
9. OTHER BUSINESS
Include any additional items discussed that were not on the original agenda. Add brief descriptions and outcomes of those discussions.
ADDITIONAL ITEMS | DESCRIPTION |  | OUTCOMES
Team building | Discussed the upcoming team-building retreat |  | Team expressed excitement and shared ideas.
10. UPCOMING DEADLINES
List upcoming project deadlines, milestones, or important dates.
TASKS AND MILESTONES
Completion of Development Phase
Marketing Campaign
11. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
Meeting concluded with a summary of discussions and action items.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
MM/DD/YY | Conference Room A
12. ATTACHMENTS OR SUPPORTING MATERIALS
Link or attach relevant documents, presentations, or reports discussed during the meeting.
MATERIALS
Links
13. APPROVAL AND SIGNATURES
Sign below to approve meeting minutes.
PARTICIPANT NAME |  | SIGNATURE
Name
Name
Name
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Team Minutes
PROJECT TEAM MEETING MINUTES TEMPLATE
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
MM/DD/YY
ATTENDEES
NAME |  | ROLE
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
3. PREVIOUS MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on the completion of these action items.
SUMMARY
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
4. DISCUSSION POINTS
Include a detailed discussion of each agenda item. Include key points, decisions, and information shared during the discussion. Include any presentations or visuals shared during the meeting.
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
5. ACTION ITEMS
List action items and identified during the meeting. Include responsible parties assigned to each item, due dates for each item, and note action items carried forward from previous meetings.
ACTION ITEM |  | OWNER | DUE DATE
6. DECISIONS MADE
Include a clear and concise description of decisions reached during the meeting. Include justifications or context for the decisions, if necessary.
DECISIONS
7. RISKS AND ISSUES
Discuss any new risks or issues identified during the meeting. Include mitigation strategies.
RISK OR ISSUE |  | MITIGATION STRATEGY
8. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
9. OTHER BUSINESS
Include any additional items discussed that were not on the original agenda. Add brief descriptions and outcomes of those discussions.
ADDITIONAL ITEMS | DESCRIPTION |  | OUTCOMES
10. UPCOMING DEADLINES
List upcoming project deadlines, milestones, or important dates.
TASKS AND MILESTONES
11. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
MM/DD/YY
12. ATTACHMENTS OR SUPPORTING MATERIALS
Link or attach relevant documents, presentations, or reports discussed during the meeting.
MATERIALS
Links
13. APPROVAL AND SIGNATURES
Sign below to approve meeting minutes.
PARTICIPANT NAME |  | SIGNATURE
Name
Name
Name

## – Disclaimer –
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.