## EXAMPLE - Project Phases
EXCEL PROJECT PHASES TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2029-03-12 | 2029-03-15 | 4 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2029-03-15 | 2029-03-16 | 2 | 100%
1.2 | Research | Pete S | 2029-03-15 | 2029-03-21 | 7 | 90%
1.3 | Projections | Steve L | 2029-03-16 | 2029-03-22 | 7 | 40%
1.4 | Stakeholders | Allen W | 2029-03-17 | 2029-03-22 | 6 | 70%
1.5 | Guidelines | Malik M | 2029-03-18 | 2029-03-22 | 5 | 60%
1.6 | Project Initiation | Malik M | 2029-03-23 | 2029-03-23 | 1 | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2029-03-24 | 2029-03-28 | 5 | 5%
2.2 | Budget | Allen W | 2029-03-29 | 2029-04-02 | 5 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%
5 | Closure
5.1 | Write Punchlist | Steve L |  |  |  | 0%
5.2 | Create Budget Report | Allen W |  |  |  | 0%
5.3 | Postmortem Meeting | Malik M |  |  |  | 0%
5.4 | Store Deliverables | Malik M |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Phases
PROJECT PHASES TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 100%
1.2 | [5 empty] | 0%
1.3 | [5 empty] | 0%
1.4 | [5 empty] | 0%
1.5 | [5 empty] | 0%
1.6 | [5 empty] | 0%
1.7 | [5 empty] | 0%
2
2.1 | [5 empty] | 0%
2.2 | [5 empty] | 0%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
2.5 | [5 empty] | 0%
2.6 | [5 empty] | 0%
2.7 | [5 empty] | 0%
2.8 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.4 | [5 empty] | 0%
3.5 | [5 empty] | 0%
3.6 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%
4.5 | [5 empty] | 0%
4.6 | [5 empty] | 0%
5
5.1 | [5 empty] | 0%
5.2 | [5 empty] | 0%
5.3 | [5 empty] | 0%
5.4 | [5 empty] | 0%
5.5 | [5 empty] | 0%
5.6 | [5 empty] | 0%
5.7 | [5 empty] | 0%
MILESTONE 1
Description
MILESTONE 2
Description
MILESTONE 3
Description
MILESTONE 4
Description
MILESTONE 5
Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.