## EXAMPLE Marketing Report
MARKETING CAMPAIGN REPORT TEMPLATE
ACTIVITY | STATUS | ASSIGNED TO | START DATE | END DATE | NOTES
PHASE 1: PLANNING
Establish Goals | In Progress | Lori G. | MM/DD/YY | MM/DD/YY
Determine Target Audience | Complete | Denis V. | MM/DD/YY | MM/DD/YY
Develop Creative Concept | On Hold | Denis V.
Identify Marketing Channels | Overdue | Denis V.
Budget and Financial Projection | In Progress | Lori G.
Set Up Campaign Calendar | In Progress | Lori G.
Develop Plan for Testing | In Progress | Brooklyn R.
Creative Brief | Complete | Brooklyn R.
PHASE 2: CREATIVE DEVELOPMENT
Message Planning | Not Started | Denis V.
Create Marketing Assets | Not Started | Denis V.
Gather Customer Testimonials | On Hold
Other | On Hold
PHASE 3: PROMOTION PLAN
Email Campaign | Overdue | Lori G.
Social Media | Complete | Lori G.
Sales Outreach | Not Started | Brooklyn R.
Other | On Hold
PHASE 4: TESTING
Split Testing | On Hold | Brooklyn R.
Results Analysis | Overdue | Denis V.
Plan Refinement | Not Started
Other | Not Started
PHASE 5: LAUNCH
Channel A | Complete
Channel B | In Progress
Channel C | In Progress
Channel D | In Progress
PHASE 6: MEASUREMENT
Key Metrics Channel A | Not Started
Key Metrics Channel B | Not Started
Performance Evaluation | Not Started
Plan Refinement | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Marketing Report
MARKETING CAMPAIGN REPORT TEMPLATE
ACTIVITY | STATUS | ASSIGNED TO | START DATE | END DATE | NOTES
PHASE 1: NAME
Activity | In Progress |  | MM/DD/YY | MM/DD/YY
Activity | Complete |  | MM/DD/YY | MM/DD/YY
Activity | On Hold
Activity | Overdue
In Progress
In Progress
In Progress
Complete
PHASE 2: NAME
Activity | Not Started
Activity | Not Started
On Hold
On Hold
PHASE 3: NAME
Activity | Overdue
Complete
Not Started
On Hold
PHASE 4: NAME
Activity | On Hold
Overdue
Not Started
Not Started
PHASE 5: NAME
Activity | Complete
In Progress
In Progress
In Progress
PHASE 6: NAME
Activity | Not Started
Not Started
Not Started
Not Started

## Dropdown Keys - DO NOT DELETE
Dropdown Keys - DO NOT DELETE
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.