## EXAMPLE - Project Phases
PROJECT PHASES TEMPLATE – EXAMPLE
PROJECT NAME | [5 empty] | PROJECT MANAGER
Project Alpha | [5 empty] | Vada M.
PROJECT DELIVERABLE | [5 empty] | START DATE
00/00/0000
SCOPE STATEMENT | [5 empty] | END DATE
00/00/0000
OVERALL PROGRESS
20%
WBS No. | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
1 | PROJECT CONCEPTION AND INITIATION |  | 2029-01-02 | 2029-02-09 | 39 | Not Started | High
1.1 | – Project Charter | Chloe L. | 2029-01-02 | 2029-01-11 | 10 | In Progress | Medium
1.1.1 | –– Project Charter Revisions | Kennedy K. | 2029-01-07 | 2029-01-11 | 5 | Complete | Low
1.2 | – Research | Alex B. | 2029-01-10 | 2029-02-23 | 45 | Needs Review
1.3 | – Projections | Frank M. | 2029-01-10 | 2029-01-20 | 11 | Approved
1.4 | – Stakeholders |  | 2029-01-16 | 2029-01-29 | 14 | Overdue
1.5 | – Guidelines | Kennedy K. | 2029-01-19 | 2029-02-01 | 14 | On Hold
1.6 | – Project Initiation | Jacob V. | 2029-01-22 | 2029-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING |  | 2029-01-28 | 2029-02-14 | 18
2.1 | – Scope & Goal Setting | Frank M. | 2029-01-28 | 2029-02-06 | 10
2.2 | – Budget | Jacob V. | 2029-01-31 | 2029-02-02 | 3
2.3 | – Communication Plan | Valerie C. | 2029-02-04 | 2029-02-12 | 9
2.4 | – Risk Management | Chloe L. | 2029-02-06 | 2029-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION |  | 2029-02-18 | 2029-03-26 | 37
3.1 | – Status & Tracking | Rebecca H. | 2029-02-18 | 2029-02-20 | 3
3.2 | – KPIs | Chloe L. | 2029-02-18 | 2029-02-23 | 6
3.2.1 | –– Monitoring | Frank M. | 2029-02-18 | 2029-02-26 | 9
3.2.2 | –– Forecasts | Alex B. | 2029-02-21 | 2029-02-23 | 3
3.3 | – Project Updates | Emily H. | 2029-02-22 | 2029-02-23 | 2
3.3.1 | –– Chart Updates | Kennedy K. | 2029-02-25 | 2029-03-26 | 30
4 | PROJECT PERFORMANCE / MONITORING |  | 2029-02-25 | 2029-03-26 | 30
4.1 | – Project Objectives | Kennedy K. | 2029-02-25 | 2029-02-28 | 4
4.2 | – Quality Deliverables | Alex B. | 2029-02-26 | 2029-03-03 | 6
4.3 | – Effort & Cost Tracking | Jacob V. | 2029-02-25 | 2029-03-06 | 10
4.4 | – Project Performance | Chloe L. | 2029-03-03 | 2029-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Phases
PROJECT PHASES TEMPLATE
PROJECT NAME | [5 empty] | PROJECT MANAGER
PROJECT DELIVERABLE | [5 empty] | START DATE
00/00/0000
SCOPE STATEMENT | [5 empty] | END DATE
00/00/0000
OVERALL PROGRESS
0%
WBS No. | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
1
1.1
1.2
1.3
1.4
1.5
1.6
1.7
2
2.1
2.2
2.3
2.4
3
3.1
3.2
3.3
3.4
3.5
3.6
4
4.1
4.2
4.3
4.4

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
PRIORITY | STATUS
Low | Not Started
Medium | In Progress
High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.