## EXAMPLE Ad Agency Campaign
ADVERTISING AGENCY CAMPAIGN TIMELINE TEMPLATE EXAMPLE
CAMPAIGN NAME | Project Omega | START DATE | 2027-01-01
PROJECT MANAGER | Kirk Caskey | Enter your start date above and the timeline's months will populate. Move and edit your key date markers as needed.
MONTH 1: CAMPAIGN PREPARATION AND KICKOFF |  | MONTH 2: CAMPAIGN EXECUTION AND MONITORING |  | MONTH 3: FINALIZATION
2027-01-01 |  | 2027-02-01 |  | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
START DATE = DATE(YEAR([CAMPAIGN NAME]), MONTH([CAMPAIGN NAME])+1, DAY([CAMPAIGN NAME]))
TODAY
Market Research Kickoff • 1/1
Paid Media Buying• 2/1
MILESTONE: 3/1
Campaign Wrap-Up and Final Assessment Report
Creative Briefing • 1/4
Content Strategy Planning • 1/13
Website Landing Page Design • 1/19
Design Mock-Ups • 1/16
Social Media Teasers • 1/22
Press Release and Influencer Partnership Outreach • 1/28
Brand Message Workshops • 1/7
Ad Creative Testing• 2/4
Email Campaign Launch• 2/7
Campaign Go-Live • 2/10
Customer Feedback Collective• 2/13
Performance Analytics Review• 2/16
Community Engagement Event • 2/19
Mid-Campaign Strategy Review• 2/22
Ad Re-Target Adjustments • 2/25

## BLANK Ad Agency Campaign Time
ADVERTISING AGENCY CAMPAIGN TIMELINE TEMPLATE
CAMPAIGN NAME | Project Name | START DATE | 2027-01-01
PROJECT MANAGER | Name | Enter your start date above and the timeline's months will populate. Move and edit your key date markers as needed.
MONTH 1: Title |  | MONTH 2: Title |  | MONTH 3: Title
2027-01-01 |  | 2027-02-01 |  | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
Formulas:
START DATE = DATE(YEAR([CAMPAIGN NAME]), MONTH([CAMPAIGN NAME])+1, DAY([CAMPAIGN NAME]))
MONTH 3: Title = DATE(YEAR([START DATE]), MONTH([START DATE])+1, DAY([START DATE]))
TODAY
Item • X/X
Item • X/X
MILESTONE: X/X
Content
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X
Item • X/X

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.