## EXAMPLE Agile Product Req
AGILE PRODUCT REQUIREMENTS TEMPLATE EXAMPLE
NAME |  | Product Beta Tracking System |  |  | START DATE | END DATE | OVERALL PROGRESS
PROJECT MANAGER |  | Brent Williams |  |  | 2031-09-02 | 2031-10-10 | 35%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Alex B. |  | 2031-09-03 | 2031-09-13 | 11 | Complete
No | Feature 1 |  | Frank C. |  | 2031-09-03 | 2031-09-07 | 5 | Complete
Yes | Feature 2 |  | Jacob S. |  | 2031-09-07 | 2031-09-12 | 6 | Not Started
No | Feature 3 |  | Jacob S. |  | 2031-09-09 | 2031-09-13 | 5 | In Progress
No | SPRINT 2 |  | Jacob S. |  | 2031-09-16 | 2031-09-24 | 9 | Complete
Yes | Feature 4 |  | Alex B. |  | 2031-09-16 | 2031-09-17 | 2 | Approved
No | Feature 5 |  | Frank C. |  | 2031-09-17 | 2031-09-21 | 5 | On Hold
No | Feature 6 |  | Shari W. |  | 2031-09-22 | 2031-09-24 | 3 | Complete
No | SPRINT 3 |  | Shari W. |  | 2031-09-24 | 2031-10-05 | 12 | Not Started
No | Feature 7 |  | Alex B. |  | 2031-09-24 | 2031-09-29 | 6 | Not Started
No | Feature 8 |  | Kennedy K. |  | 2031-09-27 | 2031-10-02 | 6 | Not Started
No | Feature 9 |  | Jacob S. |  | 2031-10-02 | 2031-10-05 | 4 | Not Started
REQUIREMENTS
1. USER STORY
As a customer, I want to be able to track my order status so that I can plan accordingly.
ACCEPTANCE CRITERIA | • The customer should be able to view real-time order status updates. • Notifications should be sent for significant status changes.
2. DESCRIPTION
FEATURE / REQUIREMENT NAME | Order Tracking System
DESCRIPTION | Develop a system that allows customers to track their order status from placement to delivery. |  |  | PRIORITY | High
ESTIMATION | 8 story points
3. DEPENDENCIES
DEPENDENT USER STORIES | None
EXTERNAL DEPENDENCIES | Integration with courier service APIs for real-time updates.
4. ACCEPTANCE CRITERIA
CRITERIA 1 | Customers can see the current status (e.g., processing, shipped, delivered) when they log in.
CRITERIA 2 | Notifications are sent via email and mobile app push notifications.
5. ASSUMPTIONS AND CONSTRAINTS
ASSUMPTIONS
Customers have stable internet connections for real-time updates.
CONSTRAINTS
Budget allocation for third-party API integration is limited.
6. RISKS AND MITIGATION
RISK |  | IMPACT |  | MITIGATION
Potential delays in API integration from courier services. |  | Could delay the real-time tracking feature rollout. |  | Explore alternative courier APIs and develop a fallback plan.
7. ITERATION / RELEASE PLAN
ITERATION: Sprint 5
USER STORIES INCLUDED | Order Tracking System, User Profile Enhancements
ESTIMATED COMPLETION DATE | End of this sprint
8. REVIEW AND RETROSPECTIVE NOTES
REVIEW NOTES | Order tracking system implemented successfully. Some users reported delayed notifications.
RETROSPECTIVE | Improve notification system performance for future sprints.
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
START DATE = MIN([START DATE, row below]:G10)
END DATE = MAX([END DATE, row below]:H10)

## BLANK Agile Product Req
AGILE PRODUCT REQUIREMENTS TEMPLATE
NAME |  | Name |  |  | START DATE | END DATE | OVERALL PROGRESS
PROJECT MANAGER |  | Name
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
Yes | [7 empty] | Complete
No | [7 empty] | Complete
Yes | [7 empty] | Not Started
No | [7 empty] | In Progress
Yes | [7 empty] | Complete
Yes | [7 empty] | Approved
Yes | [7 empty] | On Hold
Yes | [7 empty] | Complete
Yes | [7 empty] | Not Started
Yes | [7 empty] | Not Started
Yes | [7 empty] | Not Started
Yes | [7 empty] | Not Started
REQUIREMENTS
1. USER STORY
As a [user type], I want [goal] so that [reason/benefit].
ACCEPTANCE CRITERIA | Specify conditions for User Story completion.
2. DESCRIPTION
FEATURE / REQUIREMENT NAME | Name of the feature or requirement
DESCRIPTION | Detailed explanation of the feature |  |  | PRIORITY | Medium
ESTIMATION | Story points
3. DEPENDENCIES
DEPENDENT USER STORIES | Specify conditions for User Story completion.
EXTERNAL DEPENDENCIES | Specify conditions for User Story completion.
4. ACCEPTANCE CRITERIA
CRITERIA 1 | Specific conditions for each requirement to be considered met
CRITERIA 2 | Specific conditions for each requirement to be considered met
CRITERIA 3 | Specific conditions for each requirement to be considered met
5. ASSUMPTIONS AND CONSTRAINTS
ASSUMPTIONS
Assumption 1
Assumption 2
Assumption 3
Assumption 4
CONSTRAINTS
Constraints 1
Constraints 2
Constraints 3
Constraints 4
6. RISKS AND MITIGATION
RISK |  | IMPACT |  | MITIGATION
Identify potential risks or uncertainties |  | Assess the potential impact on the project |  | Strategy to mitigate the risk
7. ITERATION / RELEASE PLAN
ITERATION: Iteration number or release milestone
USER STORIES INCLUDED | List of user stories included in this iteration
ESTIMATED COMPLETION DATE | Expected completion date
8. REVIEW AND RETROSPECTIVE NOTES
REVIEW NOTES | Feedback or observations after completion
RETROSPECTIVE | Lessons learned or areas for improvement

## Key - DO NOT DELETE
KEY - DO NOT DELETE
High | STATUS | YES / NO
Medium | Not Started | Yes
Low | In Progress | No
Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.