## EXAMPLE Compliance Risk Mgmt
COMPLIANCE RISK MANAGEMENT PLAN TEMPLATE
PROJECT OWNERSHIP
PROJECT NAME | Design and Construction of New Company Headquarters
PROJECT OVERVIEW | The project involves designing and constructing a new headquarters building for Anderson Consulting from start to finish.
PROJECT MANAGER | Marie Gonzalez
CONTACT INFO
PHONE | EMAIL |  | MAILING ADDRESS
000-000-0000 |  |  | Street, City, State, ZIP
VERSION
VERSION |  | DATE | AUTHOR
1.1.3 |  | 03/29/20XX | Timothy Roberts
REASON
Work on the design for the building is still ongoing.
SECTIONS IMPACTED
SECTION TITLE |  | AMENDMENT
Design |  | Amendment #2
Site Preparation |  | Amendment #2
DISTRIBUTION
DELIVERY METHOD |  | ISSUE DATE | ISSUED TO
Email |  | 03/30/20XX | Design Leader
Email |  | 03/30/20XX | Site Preparation Leader
EXECUTIVE SUMMARY
RISK ANALYSIS AND EVALUATION PROCESS
Over a period of four months, a team from Anderson Consulting held both in-person and online meetings to discuss the design and construction of their new company headquarters, as well as to develop an overall contingency plan for the project. The initial draft of the contingency plan was developed by the entire team, while the specific details were refined as various company departments reviewed and adjusted it.
DEVELOPMENT OF RISK PREVENTION MITIGATION STRATEGIES PROCESS
The project team at Anderson Consulting formed breakout groups to analyze various identified risks to the project and to develop mitigation strategies and contingency plans. Each of the tentative contingency plans were reviewed by the larger team, as well as by company leaders from departments that would be involved in the plan.
REVIEW SCHEDULE, PROCESS, AND RESPONSIBLE PARTIES
All versions of the contingency plan document, including the initial draft, are reviewed by the overall contingency planning team, the head of the team, the construction project manager, and each department head within Anderson Consulting. Approval from each of these parties is required for every version of the plan.
RISK MANAGEMENT ROLES AND RESPONSIBILITIES
NAME |  | ROLE | RESPONSIBILITIES
Brooklyn Jansen |  | Construction Project Lead | Overseeing the design and construction of the headquarters
Mateus Tobin |  | Contingency Plan Team Lead | Overseeing the initial and ongoing work of the contingency plan team
RISK REPORTING PROCESS
Each new version of the Plan is shared with company leaders, including department heads and project managers, to ensure alignment with overall company goals and objectives. The plan is also shared with the entire staff to raise awareness of potential risks and contingency procedures.
RISK ASSESSMENT
RISK IDENTIFICATION
RISK OVERVIEW |  |  | EVENT OR THREAT TRIGGERS
The construction project materials supervisor and her team will track the timing for material needs, purchases, and delivery schedules. They will develop contingency plans for alternative material sources in case of potential supply chain issues. |  |  | The construction project materials supervisor will note any significant delay in the scheduled delivery of materials.
RISK REGISTER
IDENTIFIED RISK |  | CURRENT STATUS | RISK MITIGATION STRATEGIES
The architectural firm's delays in finalizing the design cause project timeline setbacks. |  | On schedule | The construction project lead communicates constantly with the architectural firm; the company has hired an assistant to serve as a liaison and handle the firm's needs and questions.
Delays in obtaining any required permits for site work and construction can cause setbacks in the project timeline. |  | No delays | The construction project lead has assigned an assistant to track and monitor the status of all permits and to work with the architectural and construction contractors.
The purchase and delivery of certain construction materials may be delayed, which could impact the project timeline. |  | No delays | The construction project materials supervisor and her team will track when materials are needed, purchased, and scheduled for delivery, and will develop contingency plans for additional sources of materials in case of potential supply chain issues.
Financing issues cause delays in payments for ongoing design and construction work. |  | No delays | The company has obtained preliminary approval for all financing, and the CFO is responsible for working with financing sources to obtain all necessary information for each phase of financing.
CONTINGENCY ANALYSIS AND EVALUATION
Complete the following for each IDENTIFIED RISK. See MATRIX above.
IDENTIFIED RISK |  | RISK GRADE | POTENTIAL IMPACT
The architectural firm's delays in finalizing the design cause project timeline setbacks. |  | C | Delaying the start of construction work may affect the financing rates.
Delays in obtaining any required permits for site work and construction can cause setbacks in the project timeline. |  | B | A delay in completing the project could have an impact on the rates of financing and the availability of the building.
The purchase and delivery of certain construction materials may be delayed. |  | C | Delays in certain parts of construction may not affect the overall completion date of the building, but could still impact financing rates.
Financing issues cause delays in payments for ongoing design and construction work. |  | D | Delays in financing may not necessarily delay the overall building completion, even if certain parts of the construction are delayed.
MITIGATION
Complete the following for each IDENTIFIED RISK. See MITIGATION CHART above.
IDENTIFIED RISK | The architectural firm's delays in finalizing the design cause project timeline setbacks.
GRADE | A | MITIGATION ACTION: Preventative or Contingency? | Preventative
BUDGETARY IMPLICATIONS |  | Moderate
STAKEHOLDERS RESPONSIBLE |  | Construction Project Lead
IDENTIFIED RISK | Delays in obtaining any required permits for site work and construction can cause setbacks in the project timeline.
GRADE | B | MITIGATION ACTION: Preventative or Contingency? | Preventative
BUDGETARY IMPLICATIONS |  | Moderate
STAKEHOLDERS RESPONSIBLE |  | Construction Project Lead
IDENTIFIED RISK | The purchase and delivery of certain construction materials may be delayed.
GRADE | B | MITIGATION ACTION: Preventative or Contingency? | Preventative and Contingency
BUDGETARY IMPLICATIONS |  | Low/moderate
STAKEHOLDERS RESPONSIBLE |  | Construction Project Materials Supervisor
IDENTIFIED RISK | Financing issues cause delays in payments for ongoing design and construction work.
GRADE | B | MITIGATION ACTION: Preventative or Contingency? | Preventative
BUDGETARY IMPLICATIONS |  | Severe
STAKEHOLDERS RESPONSIBLE |  | Chief Financial Officer
RISK MONITORING
REVIEW OF RISKS AND ISSUES ¦ check for issues that may have escalated
REVIEW FREQUENCY
The contingency plan lead reviews the plan, risks, and issues every week and discusses them with the construction and company leaders every two weeks.
PARTIES RESPONSIBLE FOR REVIEWING
Contingency Plan Lead; Construction Project Lead; Construction Materials Lead; CFO; Company Executives
MONITORING
MONITORING FREQUENCY
The contingency plan lead continually monitors issues.
PARTIES RESPONSIBLE FOR MONITORING
Contingency Plan Lead
REPORTING
REPORTING FREQUENCY
The contingency plan lead reports any issues or updates to the plan to the contingency plan team, as well as the leaders of construction and the company, on a weekly basis.
PARTIES RESPONSIBLE FOR REPORTING
Contingency Plan Lead
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Compliance Risk Mgmt
COMPLIANCE RISK MANAGEMENT PLAN TEMPLATE
PROJECT OWNERSHIP
PROJECT NAME
PROJECT OVERVIEW
PROJECT MANAGER
CONTACT INFO
PHONE | EMAIL |  | MAILING ADDRESS
VERSION
VERSION |  | DATE | AUTHOR
REASON
SECTIONS IMPACTED
SECTION TITLE |  | AMENDMENT
DISTRIBUTION
DELIVERY METHOD |  | ISSUE DATE | ISSUED TO
EXECUTIVE SUMMARY
RISK ANALYSIS AND EVALUATION PROCESS
DEVELOPMENT OF RISK PREVENTION MITIGATION STRATEGIES PROCESS
REVIEW SCHEDULE, PROCESS, AND RESPONSIBLE PARTIES
RISK MANAGEMENT ROLES AND RESPONSIBILITIES
NAME |  | ROLE | RESPONSIBILITIES
RISK REPORTING PROCESS
RISK ASSESSMENT
RISK IDENTIFICATION
RISK OVERVIEW |  |  | EVENT OR THREAT TRIGGERS
RISK REGISTER
IDENTIFIED RISK |  | CURRENT STATUS | RISK MITIGATION STRATEGIES
CONTINGENCY ANALYSIS AND EVALUATION
Complete the following for each IDENTIFIED RISK. See MATRIX above.
IDENTIFIED RISK |  | RISK GRADE | POTENTIAL IMPACT
MITIGATION
Complete the following for each IDENTIFIED RISK. See MITIGATION CHART above.
IDENTIFIED RISK
GRADE |  | MITIGATION ACTION: Preventative or Contingency?
BUDGETARY IMPLICATIONS
STAKEHOLDERS RESPONSIBLE
IDENTIFIED RISK
GRADE |  | MITIGATION ACTION: Preventative or Contingency?
BUDGETARY IMPLICATIONS
STAKEHOLDERS RESPONSIBLE
IDENTIFIED RISK
GRADE |  | MITIGATION ACTION: Preventative or Contingency?
BUDGETARY IMPLICATIONS
STAKEHOLDERS RESPONSIBLE
IDENTIFIED RISK
GRADE |  | MITIGATION ACTION: Preventative or Contingency?
BUDGETARY IMPLICATIONS
STAKEHOLDERS RESPONSIBLE
RISK MONITORING
REVIEW OF RISKS AND ISSUES ¦ check for issues that may have escalated
REVIEW FREQUENCY
PARTIES RESPONSIBLE FOR REVIEWING
MONITORING
MONITORING FREQUENCY
PARTIES RESPONSIBLE FOR MONITORING
REPORTING
REPORTING FREQUENCY
PARTIES RESPONSIBLE FOR REPORTING

## Rating Keys - Do Not Delete -
RATING KEYS - DO NOT DELETE
RISK MATRIX | [5 empty] | MITIGATION BASED UPON GRADE
|  | IMPACT |  |  |  | GRADE | POSSIBLE ACTION
|  | LOW | MEDIUM | HIGH | EXTREME | A | As a top priority, mitigation actions that decrease both the likelihood and severity of this risk should be identified and implemented during the project planning phase and monitored throughout the project lifecycle.
LIKELIHOOD | LOW | N | D | C | A | B | Mitigation actions that decrease both the likelihood and severity of this risk should be identified and implemented during the project planning phase and monitored throughout the project lifecycle.
| MEDIUM | D | C | B | A | C | Mitigation actions that decrease the likelihood of this risk should be identified and costed for potential execution. These actions should be monitored throughout the project lifecycle.
| HIGH | C | B | A | A | D | Mitigation actions that decrease the likelihood of this risk should be identified and costed for potential execution. These actions may not need to be regularly reviewed unless the risk grading increases over time.
[6 empty] | N | Note the risk only if the risk grading increases over time.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.