## BLANK - Project Implementaion
PROJECT IMPLEMENTATION PLAN TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | START DATE | END DATE | DURATION | OVERALL PROGRESS
0%
PROJECT DELIVERABLE
TASKS | OWNER | START DATE | DUE DATE | DURATION | STATUS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Phase 1.
Phase 2.
Phase 3.
Phase 4.
Phase 5.
CLICK HERE TO CREATE IN SMARTSHEET

## SAMPLE - Project Implementation
PROJECT IMPLEMENTATION PLAN TEMPLATE
PROJECT TITLE
Charging Station Beta
PROJECT MANAGER |  | START DATE | END DATE | DURATION | OVERALL PROGRESS
Kirk Caskey |  | 2031-01-16 | 2031-04-21 | 96 | 35%
PROJECT DELIVERABLE
TASKS | OWNER | START DATE | DUE DATE | DURATION | STATUS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Phase 1. Feasibility Study |  | 2031-01-16 | 2031-02-25 | 41 | Complete
Survey potential locations | Name | 2031-01-16 | 2031-01-21 | 6 | Complete | bar: WEEK 1 F to WEEK 2 F
Conduct a market analysis | Name | 2031-01-31 | 2031-02-05 | 6 | Complete
Estimate the initial investment | Name | 2031-02-05 | 2031-02-15 | 11 | Complete | bar: WEEK 2 M to WEEK 3 R
Phase 2. Design and Development |  | 2031-01-22 | 2031-02-25 | 35 | In Progress
Finalize the designs |  | 2031-01-22 | 2031-01-29 | 8 | Overdue | bar: WEEK 2 M to WEEK 3 R
Develop software solutions |  | 2031-01-28 | 2031-01-31 | 4 | In Progress | bar: WEEK 2 M to WEEK 3 R
Secure the required permits |  | 2031-01-29 | 2031-02-25 | 28 | Not Started | bar: WEEK 3 F
Phase 3. Pilot Testing |  | 2031-02-28 | 2031-03-16 | 17 | In Progress
Identify a limited region for installation |  | 2031-02-28 | 2031-03-01 | 2 | On Hold | bar: WEEK 4 M to WEEK 5 F
Collect user feedback |  | 2031-02-28 | 2031-03-04 | 5 | Needs Review
Address any technical glitches |  | 2031-03-01 | 2031-03-16 | 16 | Approved
Phase 4. Full-Scale Rollout |  | 2031-03-16 | 2031-04-16 | 32
Launch multiple marketing campaigns |  | 2031-03-16 | 2031-03-17 | 2
Begin a phased installation |  | 2031-03-18 | 2031-03-20 | 3
Train personnel on maintenance |  | 2031-03-24 | 2031-04-16 | 24
Phase 5. Operational Management |  | 2031-03-24 | 2031-04-21 | 29
Monitor functionality and troubleshoot |  | 2031-03-24 | 2031-03-26 | 3
Collect and analyze the data |  | 2031-03-26 | 2031-04-05 | 11
Regularly update software solutions |  | 2031-04-06 | 2031-04-21 | 16

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.