## EXAMPLE - Risk Assessment
SIMPLE COMPLIANCE RISK ASSESSMENT TEMPLATE EXAMPLE
PROJECT ID | PROJECT NAME |  |  | PROJECT MANAGER
1234 | PROJECT OMEGA |  |  | LORI GARCIA
[5 empty] | RISK ASSESSMENT | [5 empty] | POST-MITIGATION |  |  | JUDGEMENT
REF / ID | TOPIC | RISK | CONTROL ENVIRONMENT | CONTROL ACTIVITIES | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | MITIGATIONS / WARNINGS / REMEDIES | INFORMATION AND COMMUNICATIONS | CONTROLS PRESENT? | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED? | COMMENTS AND NOTES
1.1 | Disaster recovery (DR) | Not having data backup and verification capabilities physically on the premises in the event of a disaster. | Duplicate off-premises data center so that one is on site and we have an accurate and reliable data redundancy between the two, in the event of a natural disaster. | Set recovery plan objectives. | ACCEPTABLE | POSSIBLE | LOW | Distinct data center redundancy testing. | IT departmental meeting on PII and GDPR standards. | YES | ACCEPTABLE | IMPROBABLE | LOW | YES | Notes
1.2 | Data integration |  |  |  | TOLERABLE | POSSIBLE | MEDIUM |  |  | NO | ACCEPTABLE | IMPROBABLE | LOW | YES | Notes
1.3 | Access risk |  |  |  | UNDESIRABLE | PROBABLE | HIGH |  |  | YES | TOLERABLE | POSSIBLE | MEDIUM | YES | Notes
2.1 | Monitor regulatory compliance |  |  |  | INTOLERABLE | PROBABLE | EXTREME |  |  | YES | UNDESIRABLE | PROBABLE | HIGH | NO | Notes
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Risk Assessment
SIMPLE COMPLIANCE RISK ASSESSMENT TEMPLATE
PROJECT ID | PROJECT NAME |  |  | PROJECT MANAGER
[5 empty] | RISK ASSESSMENT | [5 empty] | POST-MITIGATION |  |  | JUDGEMENT
REF / ID | TOPIC | RISK | CONTROL ENVIRONMENT | CONTROL ACTIVITIES | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | MITIGATIONS / WARNINGS / REMEDIES | INFORMATION AND COMMUNICATIONS | CONTROLS PRESENT? | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED? | COMMENTS AND NOTES
[5 empty] | ACCEPTABLE | POSSIBLE | LOW |  |  | YES | ACCEPTABLE | IMPROBABLE | LOW | YES
[5 empty] | TOLERABLE | POSSIBLE | MEDIUM |  |  | NO | ACCEPTABLE | IMPROBABLE | LOW | YES
[5 empty] | UNDESIRABLE | PROBABLE | HIGH |  |  | YES | TOLERABLE | POSSIBLE | MEDIUM | YES
[5 empty] | INTOLERABLE | PROBABLE | EXTREME |  |  | YES | UNDESIRABLE | PROBABLE | HIGH | NO
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES

## Matrix Key - DO NOT DELETE -
RISK RATING KEY |  | LOW | MEDIUM | HIGH | EXTREME
|  | ACCEPTABLE | ALARP (as low as reasonably practicable) | GENERALLY UNACCEPTABLE | INTOLERABLE
|  | OK TO PROCEED | TAKE MITIGATION EFFORTS | SEEK SUPPORT | PLACE ON HOLD
|  | SEVERITY |  |  |  | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED? | CONTROLS PRESENT?
|  | ACCEPTABLE | TOLERABLE | UNDESIRABLE | INTOLERABLE | ACCEPTABLE | IMPROBABLE | LOW | YES | YES
|  | LITTLE TO NO EFFECT | EFFECTS ARE FELT, BUT NOT CRITICAL TO OUTCOME | SERIOUS IMPACT TO THE COURSE OF ACTION AND OUTCOME | COULD RESULT IN DISASTER | TOLERABLE | POSSIBLE | MEDIUM | NO | NO
LIKELIHOOD | IMPROBABLE | LOW | MEDIUM | MEDIUM | HIGH | UNDESIRABLE | PROBABLE | HIGH
| RISK IS UNLIKELY TO OCCUR |  |  |  |  | INTOLERABLE |  | EXTREME
| POSSIBLE | LOW | MEDIUM | HIGH | EXTREME
RISK WILL LIKELY OCCUR
| PROBABLE | MEDIUM | HIGH | HIGH | EXTREME
RISK WILL OCCUR
|  | ACCEPTABLE | TOLERABLE | UNDESIRABLE | INTOLERABLE
| IMPROBABLE | LOW | MEDIUM | MEDIUM | HIGH
| POSSIBLE | LOW | MEDIUM | HIGH | EXTREME
| PROBABLE | MEDIUM | HIGH | HIGH | EXTREME

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.