## EXAMPLE Software Plan
SOFTWARE IMPLEMENTATION PLAN TEMPLATE EXAMPLE
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PHASE: Feasibility Study |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Survey potential Locations for charging stations | Jenna P | 40 | 40 | 0 |  | 2022-03-12 | 2022-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Conduct a market analysis to identify target customer segments | Kylie R | 25 | 25 | 0 |  | 2022-03-15 | 2022-03-16 | 2 | 100%
1.2 | Estimate initial investment and potential ROI | Pete S | 100 | 100 | 0 |  | 2022-03-15 | 2022-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Survey potential Locations for charging stations | Steve L | 60 | 60 | 0 |  | 2022-03-16 | 2022-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 |  | Allen W | 40 | 40 | 0 |  | 2022-03-17 | 2022-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 |  | Malik M | 32 | 32 | 0 |  | 2022-03-18 | 2022-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 |  | Malik M | 12 | 12 | 0 |  | 2022-03-23 | 2022-03-23 | 1 | 100% | bar: WEEK 3 F
2 | PHASE: Design and Development |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Finalize designs for charging stations and accompanying infrastructure | Steve L | 80 | 70 | 10 |  | 2022-03-24 | 2022-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Develop software solutions for payment and user interface | Allen W | 60 | 40 | 20 |  | 2022-03-29 | 2022-04-02 | 5 | 66.67%
2.3 | Secure required permits and approval for installation | Malik M | 40 | 0 | 40 |  |  |  |  | 0%
2.4 |  | Malik M | 30 | 0 | 30 |  |  |  |  | 0%
3 | PHASE: Pilot Testing |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Identify a limited region for pilot installation | Pete S | 20 | 0 | 20 |  |  |  |  | 0%
3.2 | Collect user feedback on station performance and usability | Jenna P | 20 | 0 | 20 |  |  |  |  | 0%
3.2.1 | Address any technical glitches or challenges identified during the pilot | Kylie R | 8 | 0 | 8 |  |  |  |  | 0%
3.2.2 |  | Kylie R | 12 | 0 | 12 |  |  |  |  | 0%
3.3 |  | Pete S | 4 | 0 | 4 |  |  |  |  | 0%
3.3.1 |  | Malik M | 2 | 0 | 2 |  |  |  |  | 0%
4 | PHASE: Full-Scale Rollout |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Launch marketing campaigns targeting potential users | Steve L | 8 | 0 | 8 |  |  |  |  | 0%
4.2 | Begin phased installation of charging stations across target regions | Allen W | 12 | 0 | 12 |  |  |  |  | 0%
4.3 | Train personnel on station maintenance and customer support | Malik M | 8 | 0 | 8 |  |  |  |  | 0%
4.4 | Monitor station functionality and troubleshoot as needed | Malik M | 4 | 0 | 4 |  |  |  |  | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
BURNDOWN DATA |  | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833 | HOURS
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
BURNDOWN CHART
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Software Plan
SOFTWARE IMPLEMENTATION PLAN TEMPLATE
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 |  |  | 0 | 0 | 0
1.1 |  |  |  |  | 0 | bar: WEEK 1 M
1.1.1 |  |  |  |  | 0
1.2 |  |  |  |  | 0
1.3 |  |  |  |  | 0
1.4 |  |  |  |  | 0
1.5 |  |  |  |  | 0
1.6 |  |  |  |  | 0
2 |  |  | 0 | 0 | 0
2.1 |  |  |  |  | 0 | bar: WEEK 4 M
2.2 |  |  |  |  | 0
2.3 |  |  |  |  | 0
2.4 |  |  |  |  | 0
3 |  |  | 0 | 0 | 0
3.1 |  |  |  |  | 0 | bar: WEEK 7 M
3.2 |  |  |  |  | 0
3.2.1 |  |  |  |  | 0
3.2.2 |  |  |  |  | 0
3.3 |  |  |  |  | 0
3.3.1 |  |  |  |  | 0
4 |  |  | 0 | 0 | 0
4.1 |  |  |  |  | 0 | bar: WEEK 10 M
4.2 |  |  |  |  | 0
4.3 |  |  |  |  | 0
4.4 |  |  |  |  | 0
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
BURNDOWN DATA |  | TOTAL HOURS | 0 | 0 | 0 | 60 | 0 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HOURS
[10 empty] | ESTIMATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | [60 empty] | 0
[10 empty] | HRS REMAINING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BURNDOWN CHART

## Release Backlog
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES
Low |  |  | Task 1 | Description | Name | 1 | Complete
Medium | [5 empty] | 2 | Overdue
High | [5 empty] | 4 | In Progress
Low | [5 empty] | 16 | Not Started
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete
Low | [5 empty] | 1 | Complete

## User Stories or Tasks
USER STORIES OR TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Title | Task description | Name | MM/DD/YY

## Dropdown Keys - DO NOT DELETE
Dropdown Keys - DO NOT DELETE
STATUS KEY | WORK ESTIMATE IN HOURS | PRIORITY KEY
Complete | 1 | High
Overdue | 2 | Medium
In Progress | 4 | Low
Not Started | 8
16
24
40
80

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.