## EXAMPLE - ABM Project Plan
ACCOUNT-BASED MARKETING (ABM) PROJECT PLAN TEMPLATE – EXAMPLE
PROJECT ID | PROJECT NAME |  |  |  | PROJECT MANAGER |  |  | DATE OF LAST UPDATE |  | RUNNING TASK COST TOTAL
MVP4162 | CLEAR BLUE SKY SYSTEM UPGRADE |  |  |  | SASHA W. |  |  |  |  | 19326
[6 empty] | TIMELINE |  |  |  | FINANCE
TASK ID | TASK | PRIORITY | STATUS | OWNER | ASSIGNED TO | PROJECTED START DATE | PROJECTED END DATE | ACTUAL START DATE | ACTUAL END DATE | PROJECTED COST | ACTUAL COST | PROGRESS NOTES
1 | Target Account Identification | High | Not Started | [6 empty] | 6500 | 7200 | Timeline approved by exec. team
2 | Persona Development | Medium | In Progress | [6 empty] | 2875 | 3150
3 | Custom Content Creation | High | Complete | [6 empty] | 3200 | 2800 | Signed off 07/31
4 | Personalized Outreach | Medium | Needs Review | [6 empty] | 876 | 576 | Hold: pending HR review
5 | Social Engagement | High | Approved | [6 empty] | 5309 | 5600
6 | Host a Webinar | Low | Overdue
7 | On-Site Demo | Low | On Hold
8 | Collaborate on Case Studies | Low
9 | Feedback Loop with Sales
10 | Retargeting Campaign
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - ABM Project Plan
ACCOUNT-BASED MARKETING (ABM) PROJECT PLAN TEMPLATE
PROJECT ID | PROJECT NAME |  |  |  | PROJECT MANAGER |  |  | DATE OF LAST UPDATE |  | RUNNING TASK COST TOTAL
0
[6 empty] | TIMELINE |  |  |  | FINANCE
TASK ID | TASK | PRIORITY | STATUS | OWNER | ASSIGNED TO | PROJECTED START DATE | PROJECTED END DATE | ACTUAL START DATE | ACTUAL END DATE | PROJECTED COST | ACTUAL COST | PROGRESS NOTES

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.