## EXAMPLE - Agile Product Roadmap
AGILE PRODUCT ROADMAP TEMPLATE – EXAMPLE
SPRINT 0 | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6 | SPRINT 7
2031-06-01 | 2031-06-15 | 2031-06-29 | 2031-07-13 | 2031-07-27 | 2031-08-10 | 2031-08-24 | 2031-09-07
1. MARKET RESEARCH AND ANALYSIS
2. PRODUCT DESIGN AND DEVELOPMENT
3. SOFTWARE DEVELOPMENT FOR CHARGING STATIONS
4. MOBILE APP DEVELOPMENT
5. INFRASTRUCTURE AND DEPLOYMENT PLANNING
6. MARKETING AND BRANDING
7. TESTING AND QUALITY ASSURANCE
8. LAUNCH AND POST-LAUNCH ACTIVITIES
CLICK HERE TO CREATE IN SMARTSHEET
TEAM 1
TEAM 4
TEAM 2
TEAM 3
TEAM KEY
MILESTONE
00/00/00
Conduct competitor analysis.
Survey potential users for charging needs.
Analyze trends in EV usage.
Study regional EV charging infrastructure.
Develop initial design prototypes for charging units.
Optimize design for user-friendliness and efficiency.
Develop user interface for charging stations.
Integrate payment processing system.
Create monitoring system for station status.
Design user-friendly app interface.
Integrate app with charging stations.
Add features like location finder, booking, and payment.
Identify strategic locations for charging stations.
Plan logistics for station installation.
Coordinate with local authorities for permits.
Develop maintenance and servicing schedules.
Conduct field tests for charging stations.
Perform app testing on various devices.
Ensure compliance with safety standards.
Gather user feedback for improvements.
Test prototypes in controlled environments.
Iterate designs based on feedback.
Implement remote troubleshooting capabilities.
Ensure security measures for user data.
Create branding strategy.
Plan launch event and promotional activities.
Develop marketing materials and website.
Initiate social media campaigns.
Officially launch charging stations and app.
Implement continuous improvement process.
Monitor initial user interactions and feedback.
Plan for expansion and new feature additions.

## BLANK - Agile Product Roadmap
AGILE PRODUCT ROADMAP TEMPLATE
SPRINT 0 | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6 | SPRINT 7
00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00
1. Text
2. Text
3. Text
4. Text
5. Text
6. Text
7. Text
8. Text
TEAM 1
TEAM 4
TEAM 2
TEAM 3
TEAM KEY
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
Text
MILESTONE
00/00/00

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.