## EXAMPLE – Change Log Template
CHANGE LOG TEMPLATE – EXAMPLE
PROJECT NAME |  |  |  | PROJECT MANAGER |  | DATE OF LAST UPDATE
Project Beta |  |  |  | Emily Johnson |  | 00/00/0000
CHANGE NO. | CHANGE TYPE | DESCRIPTION | DATE IDENTIFIED | STATUS | PRIORITY | ASSIGNED TO | RESOLUTION EXPECTED | ACTION | AREA OF IMPACT | ESCALATION REQUIRED | DATE RESOLVED
1 | Design | Update UI for more intuitive and modern look. | 10/15/20XX | Approved | Medium | Tom Reynolds | 1 Month | Implement UI changes based on new design guidelines. | Budget | NO | 11/16/20XX
2 | Product | Resolve UI display issue on homepage. | 11/16/20XX | Open | High | Robert Cashman | 1 Week | Debug and deploy updated UI code. | Schedule | YES
3 | Documentation | Revise user manual for version 2.0. | 11/30/20XX | Approved | Medium | Tasha Meyers | 2 Weeks | Review, edit, and publish updated documentation. | Schedule | NO
|  |  |  | In Progress | Low
Rejected
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK – Change Log Template
CHANGE LOG TEMPLATE
PROJECT NAME |  |  |  | PROJECT MANAGER |  | DATE OF LAST UPDATE
CHANGE NO. | CHANGE TYPE | DESCRIPTION | DATE IDENTIFIED | STATUS | PRIORITY | ASSIGNED TO | RESOLUTION EXPECTED | ACTION | AREA OF IMPACT | ESCALATION REQUIRED | DATE RESOLVED

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS | VARIOUS
YES | Low | Open | Not Started
NO | Medium | In Progress | In Progress
| High | Approved | Complete
|  | Rejected | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.