## EXAMPLE Yearly Plan with Gantt
YEARLY PLANNING TEMPLATE WITH GANTT CHART
COMPANY / ORGANIZATION NAME |  |  | DATE
Weller Industries |  |  | MM/DD/YY
OVERVIEW
MISSION AND VALUES | Describe the company mission and values.
STRATEGIES
MARKET FOCUS | Describe the market focus.
OPERATIONAL FOCUS | Describe the operational focus.
SALES FOCUS | Describe the sales focus.
GLOBAL PRIORITIES
GOALS | OBJECTIVES | OWNER NAME | BUDGET | START DATE | END DATE | DURATION in days | STATUS | TEAM
Achievement plan 1 | Actions | Alex B. | 0 | 2028-01-16 | 2028-02-15 | 31 | ON TRACK | Team name
Feature 1 | Actions | Frank C. | 0 | 2028-01-16 | 2028-02-02 | 18 | NEEDS ATTENTION | Team name
Feature 2 | Actions | Jacob S. | 0 | 2028-01-31 | 2028-02-05 | 6 | ON TRACK | Team name
Feature 3 | Actions | Jacob S. | 0 | 2028-02-05 | 2028-02-15 | 11 | DONE
Achievement plan 2 | Actions | Jacob S. | 0 | 2028-01-22 | 2028-02-25 | 35 | DONE
Feature 1 | Actions | Alex B. | 0 | 2028-01-22 | 2028-01-29 | 8 | BEHIND
Feature 2 | Actions | Frank C. | 0 | 2028-01-28 | 2028-01-31 | 4 | ON TRACK
Feature 3 | Actions | Shari W. | 0 | 2028-01-29 | 2028-02-25 | 28 | ON TRACK
Achievement plan 3 | Actions | Shari W. | 0 | 2028-02-28 | 2028-03-16 | 18 | NEEDS ATTENTION
Feature 1 | Actions | Alex B. | 0 | 2028-02-28 | 2028-03-01 | 3 | ON TRACK
Feature 2 | Actions | Kennedy K. | 0 | 2028-02-28 | 2028-03-04 | 6 | ON TRACK
Feature 3 | Actions | Jacob S. | 0 | 2028-03-01 | 2028-03-16 | 16 | DONE
Achievement plan 4 | Actions | Jacob S. | 0 | 2028-03-16 | 2028-04-16 | 32 | DONE
Feature 1 | Actions | Jacob S. | 0 | 2028-03-16 | 2028-03-17 | 2 | DONE
Feature 2 | Actions | Jacob S. | 0 | 2028-03-18 | 2028-03-20 | 3 | DONE
Feature 3 | Actions | Alex B. | 0 | 2028-03-24 | 2028-04-16 | 24 | NEEDS ATTENTION
Achievement plan 5 | Actions | Frank C. | 0 | 2028-03-24 | 2028-04-21 | 29 | BEHIND
Feature 1 | Actions | Shari W. | 0 | 2028-03-24 | 2028-03-26 | 3 | ON TRACK
Feature 2 | Actions | Shari W. | 0 | 2028-03-26 | 2028-04-05 | 11 | ON TRACK
Feature 3 | Actions | Kennedy K. | 0 | 2028-04-06 | 2028-04-21 | 16 | ON TRACK
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Yearly Plan with Gantt
YEARLY PLANNING TEMPLATE WITH GANTT CHART
COMPANY / ORGANIZATION NAME |  |  | DATE
Name |  |  | MM/DD/YY
OVERVIEW
MISSION AND VALUES | Describe the company mission and values.
STRATEGIES
MARKET FOCUS | Describe the market focus.
OPERATIONAL FOCUS | Describe the operational focus.
SALES FOCUS | Describe the sales focus.
GLOBAL PRIORITIES
GOALS | OBJECTIVES | OWNER NAME | BUDGET | START DATE | END DATE | DURATION in days | STATUS | TEAM
|  |  | 0 |  |  |  | ON TRACK
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Keys - Do Not Delete -
STATUS KEY - DO NOT DELETE
ON TRACK
NEEDS ATTENTION
DONE
BEHIND

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.