## EXAMPLE Infrastructure PM Plan
INFRASTRUCTURE PROJECT MANAGEMENT PLAN TEMPLATE EXAMPLE
PROJECT TITLE |  |  | START DATE
Westside Waterfront Redevelopment |  |  | 2024-01-25 |  |  | PROJECT DURATION
PROJECT MANAGER |  |  | END DATE |  |  | in days
Alexandra Taylor |  |  | 2024-04-15 |  |  | 82
PROJECT SPONSOR |  |  | ACTUAL END DATE
City of New Horizons Development Authority |  |  | MM/DD
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | PLANNING | Complete | Karl Peter | 2024-01-02 | 2024-02-09 | 39
1.1 | Conduct Feasibility Study | In Progress | Makara McLean | 2024-01-02 | 2024-01-11 | 10
1.2 | Develop Initial Project Scope | In Progress | Krisa Ahmed | 2024-01-10 | 2024-02-23 | 45
1.3 | Identify Regulatory Requirements | In Progress | Krisa Ahmed | 2024-01-10 | 2024-01-20 | 11
1.4 | Risk Assessment | Complete | Karl Peter | 2024-01-16 | 2024-01-29 | 14
1.5 | Stakeholder Identification and Analysis | In Progress | Karl Peter | 2024-01-19 | 2024-02-01 | 14
1.6 | Other | Complete | Brennan Gardiner | 2024-01-22 | 2024-02-09 | 19
2 | PREPARATION | Not Started | Aila Kishimoto | 2024-01-28 | 2024-02-14 | 18
2.1 | Detailed Project Charter Development | Not Started | Brennan Gardiner | 2024-01-28 | 2024-02-06 | 10
2.2 | Finalize Project Scope and Goals | Not Started | Makara McLean | 2024-01-31 | 2024-02-02 | 3
2.3 | Develop Detailed Budget | Not Started | Makara McLean
2.4 | Communication Plan | Not Started | Makara McLean
2.5 | Detailed Risk Management Plan | Not Started | Krisa Ahmed | 2024-02-04 | 2024-02-12 | 9
2.6 | Site Assessment and Surveys | Not Started | Krisa Ahmed | 2024-02-06 | 2024-02-14 | 9
3 | PROCUREMENT | In Progress |  | 2024-02-18 | 2024-03-26 | 38
3.1 | Materials Sourcing Strategy | Complete | Brennan Gardiner | 2024-02-18 | 2024-02-20 | 3
3.2 | Vendor Selection and Contracting | Complete | Makara McLean | 2024-02-18 | 2024-02-23 | 6
3.3 | Acquire Necessary Permits and Approvals | On Hold | Makara McLean | 2024-02-18 | 2024-02-26 | 9
3.4 | Purchase Orders and Material Scheduling | In Progress | Makara McLean | 2024-02-21 | 2024-02-23 | 3
3.5 | Equipment Leasing Agreements | In Progress | Krisa Ahmed | 2024-02-22 | 2024-02-23 | 2
3.6 | Establish Logistics for Material Delivery | In Progress | Krisa Ahmed | 2024-02-25 | 2024-03-26 | 31
4 | IMPLEMENTATION | On Hold |  | 2024-02-25 | 2024-03-26 | 31
4.1 | Construction Kick-off Meeting | Not Started | Brennan Gardiner | 2024-02-25 | 2024-02-28 | 4
4.2 | Safety Training and Protocols Implementation | On Hold | Makara McLean | 2024-02-26 | 2024-03-03 | 7
4.3 | Quality Assurance and Quality Control Measures | On Hold | Makara McLean | 2024-02-27 | 2024-03-04
4.4 | Site Preparation and Groundbreaking | On Hold | Makara McLean | 2024-02-28 | 2024-03-05
4.5 | Monitoring Progress Against Schedule | On Hold | Krisa Ahmed | 2024-02-29 | 2024-03-06
4.6 | Change Management Process | On Hold | Krisa Ahmed | 2024-03-01 | 2024-03-07
4.7 | Construction Kick-off Meeting | On Hold | Krisa Ahmed | 2024-03-02 | 2024-03-08
5 | CLOSURE | On Hold |  | 2024-04-01 | 2024-04-15 | 15
5.1 | Final Inspection and Quality Verification | On Hold |  | 2024-04-01 | 2024-04-02
5.2 | Punch List Completion | On Hold |  | 2024-04-02 | 2024-04-03
5.3 | Finalize Project Documentation | On Hold |  | 2024-04-04 | 2024-04-10 | 7
5.4 | Release Final Payments and Close Contracts | On Hold |  | 2024-04-12 | 2024-04-15 | 4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Infrastructure PM Plan
INFRASTRUCTURE PROJECT MANAGEMENT PLAN TEMPLATE
PROJECT TITLE |  |  | START DATE
Title |  |  | 2024-01-25 |  |  | PROJECT DURATION
PROJECT MANAGER |  |  | END DATE |  |  | in days
Name |  |  | 2024-04-15 |  |  | 82
PROJECT SPONSOR |  |  | ACTUAL END DATE
Name |  |  | MM/DD
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | TASK | Complete |  | 2024-01-02 | 2024-02-09 | 39
1.1 | Task | In Progress |  | 2024-01-02 | 2024-01-11 | 10
1.2 |  | In Progress |  | 2024-01-10 | 2024-02-23 | 45
1.3 |  | In Progress |  | 2024-01-10 | 2024-01-20 | 11
1.4 |  | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 |  | In Progress |  | 2024-01-19 | 2024-02-01 | 14
1.6 |  | Complete |  | 2024-01-22 | 2024-02-09 | 19
2 | TASK | Not Started |  | 2024-01-28 | 2024-02-14 | 18
2.1 |  | Not Started |  | 2024-01-28 | 2024-02-06 | 10
2.2 |  | Not Started |  | 2024-01-31 | 2024-02-02 | 3
2.3 |  | Not Started
2.4 |  | Not Started
2.5 |  | Not Started |  | 2024-02-04 | 2024-02-12 | 9
2.6 |  | Not Started |  | 2024-02-06 | 2024-02-14 | 9
3 | TASK | In Progress |  | 2024-02-18 | 2024-03-26 | 38
3.1 |  | Complete |  | 2024-02-18 | 2024-02-20 | 3
3.2 |  | Complete |  | 2024-02-18 | 2024-02-23 | 6
3.3 |  | On Hold |  | 2024-02-18 | 2024-02-26 | 9
3.4 |  | In Progress |  | 2024-02-21 | 2024-02-23 | 3
3.5 |  | In Progress |  | 2024-02-22 | 2024-02-23 | 2
3.6 |  | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | TASK | On Hold |  | 2024-02-25 | 2024-03-26 | 31
4.1 |  | Not Started |  | 2024-02-25 | 2024-02-28 | 4
4.2 |  | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 |  | On Hold |  | 2024-02-27 | 2024-03-04
4.4 |  | On Hold |  | 2024-02-28 | 2024-03-05
4.5 |  | On Hold |  | 2024-02-29 | 2024-03-06
4.6 |  | On Hold |  | 2024-03-01 | 2024-03-07
4.7 |  | On Hold |  | 2024-03-02 | 2024-03-08
5 | TASK | On Hold |  | 2024-04-01 | 2024-04-15 | 15
5.1 |  | On Hold |  | 2024-04-01 | 2024-04-02
5.2 |  | On Hold |  | 2024-04-02 | 2024-04-03
5.3 |  | On Hold |  | 2024-04-04 | 2024-04-10 | 7
5.4 |  | On Hold |  | 2024-04-12 | 2024-04-15 | 4
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - Do Not Delete
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.