## EXAMPLE Annual Ops Plan
ANNUAL OPERATIONAL PLAN TEMPLATE
Fill in non-shaded cells only.
START DATE |  |  | BUSINESS NAME |  | CREATOR |  |  | TITLE
2025-01-01 |  |  | Main Street Corp. |  | Bob B. |  |  | Sr. VP
EXECUTIVE SUMMARY
Project includes responsibilities for the Alpha Client Outreach project.
PLAN DETAILS | [9 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
GOAL | STRATEGY | PROJECT NAMES + TASK TITLES | RESPONSIBLE PARTY | RESOURCES NEEDED | START DATE | END DATE | # of Days | EVIDENCE OF SUCCESS | STATUS | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Kickoff Alpha |  | CATEGORY 1 | Kim P. |  | 2025-01-05 | 2025-12-31 | 258 |  | Complete | bar: 2025-01-01 to 2025-12-01
|  | P1 Task 1 | John K. | Marketing | 2025-01-05 | 2025-05-05 | 86 |  | Complete | bar: 2025-01-01 to 2025-05-01
|  | P1 Task 2 | Robert M. |  | 2025-02-02 | 2025-03-05 | 23 |  | In progress | bar: 2025-02-01 to 2025-03-01
|  | P1 Task 3 | Virginia W. |  | 2025-07-11 | 2025-07-25 | 11 |  | Incomplete | bar: 2025-07-01
|  | P1 Task 4 |  |  | 2025-10-01 | 2025-12-31 | 66 |  | On hold | bar: 2025-10-01 to 2025-11-01
|  | P1 Task 5 |  |  | 2025-04-03 | 2025-05-01 | 21 |  | On hold | bar: 2025-04-01 to 2025-05-01
|  | P1 Task 6 |  |  | 2025-06-01 | 2025-06-15 | 10 | bar: 2025-06-01
|  | CATEGORY 2 |  |  | 2025-01-05 | 2025-12-31 | 258 | bar: 2025-01-01 to 2025-12-01
|  | P2 Task 1 |  |  | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
|  | P2 Task 2 |  |  | 2025-02-02 | 2025-03-05 | 23 | bar: 2025-02-01 to 2025-03-01
|  | P2 Task 3 |  |  | 2025-06-01 | 2025-06-05 | 4 | bar: 2025-06-01
|  | P2 Task 4 |  |  | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-11-01
|  | P2 Task 5 |  |  | 2025-04-03 | 2025-05-01 | 21 | bar: 2025-04-01 to 2025-05-01
|  | P2 Task 6 |  |  | 2025-06-01 | 2025-06-15 | 10 | bar: 2025-06-01
|  | CATEGORY 3 |  |  | 2025-01-05 | 2025-12-31 | 258 | bar: 2025-01-01 to 2025-12-01
|  | P3 Task 1 |  |  | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
|  | P3 Task 2 |  |  | 2025-02-02 | 2025-03-05 | 23 | bar: 2025-02-01 to 2025-03-01
|  | P3 Task 3 |  |  | 2025-08-02 | 2025-09-05 | 25 | bar: 2025-08-01 to 2025-09-01
|  | P3 Task 4 |  |  | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-11-01
|  | P3 Task 5 |  |  | 2025-04-03 | 2025-05-01 | 21 | bar: 2025-04-01 to 2025-05-01
|  | P3 Task 6 |  |  | 2025-06-01 | 2025-06-15 | 10 | bar: 2025-06-01
|  | CATEGORY 4 |  |  | 2025-01-05 | 2025-12-31 | 258 | bar: 2025-01-01 to 2025-12-01
|  | P4 Task 1 |  |  | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
|  | P4 Task 2 |  |  | 2025-02-02 | 2025-03-05 | 23 | bar: 2025-02-01 to 2025-03-01
|  | P4 Task 3 |  |  | 2025-07-11 | 2025-10-02 | 60 | bar: 2025-07-01 to 2025-10-01
|  | P4 Task 4 |  |  | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-11-01
|  | P4 Task 5 |  |  | 2025-04-03 | 2025-05-01 | 21 | bar: 2025-04-01 to 2025-05-01
|  | P4 Task 6 |  |  | 2025-06-01 | 2025-06-15 | 10 | bar: 2025-06-01
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
CREATOR = MIN([CREATOR, row below]:G16)
CREATOR = MIN(IF([CREATOR, row below]:G30="","",[CREATOR, row below]:G30))

## BLANK Annual Ops Plan
ANNUAL OPERATIONAL PLAN TEMPLATE
Fill in non-shaded cells only.
START DATE |  |  | BUSINESS NAME |  | CREATOR |  |  | TITLE
MM/DD/YY |  |  | Name |  | Name |  |  | Title
EXECUTIVE SUMMARY
Summary
PLAN DETAILS | [9 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
GOAL | STRATEGY | PROJECT NAMES + TASK TITLES | RESPONSIBLE PARTY | RESOURCES NEEDED | START DATE | END DATE | # of Days | EVIDENCE OF SUCCESS | STATUS | MM/DD/YY | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | CATEGORY 1 | Name |  | 0 | 0 | 0 |  | Complete | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Task |  |  |  |  | 0 |  | Complete | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  | In progress | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  | Incomplete | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  | On hold | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  | On hold | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | CATEGORY 2 |  |  | 0 | 0 | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Task |  |  |  |  | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | CATEGORY 3 |  |  | 0 | 0 | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Task |  |  |  |  | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | CATEGORY 4 |  |  | 0 | 0 | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | Task |  |  |  |  | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 0 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
CREATOR = MIN([CREATOR, row below]:G15)
CREATOR = MIN(IF([CREATOR, row below]:G29="","",[CREATOR, row below]:G29))

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.